{"text_format":"1","workbook":"xlsx","n_sheets":6,"sheets":["Выбор объекта","Настройки","Протокол","Эф. по корпусам","Эф. по подр.","График план-факт"],"not_rendered":{"charts":0,"images":3,"macros":1,"external_links":0,"defined_names":8,"comments":0,"pivot_tables":4},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Выбор объекта","index":0,"n_rows":12,"n_cols":5,"rows_kept":12,"cut":false,"hidden":false,"merged":[]}
[]
[]
[null,null,null,null,"Дата совещания"]
[null,null,null,null,{"$f":"TODAY()","v":"2022-09-20"}]
[]
[]
[null,null,null,null,"Выберите объект"]
[null,null,null,null,"НС-3. Резиденции. Уч. 26 / 6-я оч."]
[]
[]
[]
[null,null,null,null,"Если при обновлении возникает ошибка:"]

{"sheet":"Настройки","index":1,"n_rows":22,"n_cols":6,"rows_kept":22,"cut":false,"hidden":true,"merged":[]}
["Список объектов"]
["id","name",null,null,"Номер объекта","Название объекта"]
[1,"НС-3. Резиденции. Уч. 26 / 6-я оч.",null,null,{"$f":"INDEX(qObjects_change[id],MATCH('Выбор объекта'!E8,qObjects_change[name],0))","v":1},{"$f":"INDEX(qObjects_change[name],MATCH(Номер_объекта[Номер объекта],qObjects_change[id],0))","v":"НС-3. Резиденции. Уч. 26 / 6-я оч."}]
[2,"НС-3. Резиденции. Уч. 41 / 5-я оч"]
[4,"НС-3. Резиденции. Уч. 10 / 7-я оч."]
[5,"НС-1. Участки 27, 28"]
[6,"[тест] Участки 15, 18, 22"]
[7,"НС-3. Резиденции. Уч. 39, 40 / 3, 4-я оч."]
[8,"НС-3. Резиденции. Уч. 11 / 8-я оч."]
[9,"НС-1. Участки 13, 14"]
[10,"НС-1. Участки 20, 26"]
[11,"НС-3. Резиденции. Уч. 7 / 9 оч."]
[12,"НС-3. Резиденции. Уч. 1 / 10 оч."]
[13,"Парадный Ансамбль 38. уч"]
[14,"Парадный Ансамбль 40. уч"]
[15,"Парадный Ансамбль 42 уч."]
[16,"Чистое небо 14 оч."]
[17,"Стрельна / 1 оч. / 16 уч."]
[18,"Детскосельский. Этап I / 1 оч."]
[19,"Детскосельский. Этап I / 2 оч."]
[20,"Детскосельский. Этап I / 3 оч."]
[21,"Детскосельский. Этап I / 4 оч."]

{"sheet":"Протокол","index":2,"n_rows":564,"n_cols":7,"rows_kept":564,"cut":false,"hidden":false,"merged":[[7,2,7,6]]}
[null,{"$f":"\"Протокол производственного совещания №\"&WEEKNUM(дата_совещания[])&\" от \"&TEXT(дата_совещания[],\"ДД.ММ.ГГГГ\")","v":"Протокол производственного совещания №39 от 20.09.2022"}]
[null,"Заказчик ООО \"СЗ Сэтл Инвест\":","Руководитель проекта \nВедущий инженер по строительству "]
[null,"Генеральный подрядчик \nООО \"Сэтл Строй\":","Инженеры участка:"]
[null,"Подрядные организации:"]
[]
[]
[]
[null,null,"Совещание проводится каждую среду в 10:00                                                                                                                       Примечание: В случае отсутствия на еженедельном совещании, представителя Подрядчика, Генеральный подрядчик вправе начислить и взыскать штраф в размере 50 000 (Пятьдесят тысяч) рублей 00 копеек."]
[]
[null,"РЕГЛАМЕНТ  ПРОВЕДЕНИЯ СОВЕЩАНИЯ:",null,null,"Условные обозначения:"]
[null,"1. Доклад осуществляется в следующем порядке*:",null,null,null,"Не выполнено"]
[null,"1.1.Отчет о выполненной работе: План/Факт"]
[null,"1.2. План работ на следующую неделю."]
[null,"2. Расписаться в листе ознакомления с производственным совещанием."]
[]
[null,"Отчётная неделя",null,null,null,"Следующая неделя"]
[null,{"$f":"TEXT(дата_совещания[]-8,\"ДД.ММ.ГГГГ\")&\"-\"&TEXT(дата_совещания[]-1,\"ДД.ММ.ГГГГ\")","v":"12.09.2022-19.09.2022"},null,null,null,{"$f":"TEXT(дата_совещания[],\"ДД.ММ.ГГГГ\")&\"-\"&TEXT(дата_совещания[]+7,\"ДД.ММ.ГГГГ\")","v":"20.09.2022-27.09.2022"}]
[null,"Наименование работ","Подрядная организация",{"$f":"дата_совещания[]","v":"2022-09-20"},null,"Наименование работ",{"$f":"дата_совещания[]+7","v":"2022-09-27"}]
[null,null,null,"План","Факт",null,"План"]
["Названия строк","work_name.1","qBuilders.name","план_эт","факт_эт","работы","планслед_эт"]
["НС-3. Резиденции. Уч. 26 / 6-я оч. / Корпус 6.1"]
["Секция 1"]
[20,"Металлические решётки приямков в подвале","ГПК Инжпетрострой (металл)","подвал","подвал","Металлические решётки приямков в подвале"]
[21,"Металлические лестницы и ограждения в подвале","ГПК Инжпетрострой (металл)","подвал","подвал","Металлические лестницы и ограждения в подвале"]
[23,"Подготовка монолита (шлифовка стен)","ЭнергоПроектСтрой","подвал","подвал-0%","Подготовка монолита (шлифовка стен)","подвал"]
[42,"▌Фасады на балконах. Окраска 1й слой","Арсенал Строй","эт1, эт2, эт3, эт4","эт1-25%, эт2-25%, эт3-25%, эт4-25%","▌Фасады на балконах. Окраска 1й слой","эт1, эт2, эт3, эт4"]
[52,"▲ Кровля. Гидроизоляция верхний слой","СК Интеп",null,null,"▲ Кровля. Гидроизоляция верхний слой","кровля"]
[53,"▲ Кровля. Окрытие парапета","СК Интеп","кровля","кровля-0%","▲ Кровля. Окрытие парапета","кровля"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)","эт3","эт3","Вмазка коробок и квартирных щитов"]
[71,"Двери технические и МОП","ССП Групп","подвал, эт1, эт2, эт3, эт4","подвал, эт1, эт2, эт3, эт4","Двери технические и МОП"]
[76,"▌Фасады с лесов. Окраска","Арсенал Строй","эт2, эт3, эт4, кровля","эт2-0%, эт3-0%, эт4-0%, кровля-0%","▌Фасады с лесов. Окраска","эт2, эт3, эт4, кровля"]
[77,"▌Фасады НВФ. Кронштейны","Арсенал Строй","эт1","эт1","▌Фасады НВФ. Кронштейны"]
[78,"▌Фасады НВФ. Утепление","Арсенал Строй","эт1","эт1","▌Фасады НВФ. Утепление"]
[79,"▌Фасады НВФ. Направляющие","Арсенал Строй","эт1","эт1-0%","▌Фасады НВФ. Направляющие","эт1"]
[80,"▌Фасады НВФ. Монтаж керамогранита","Арсенал Строй","эт2, эт3, эт4","эт2-75%, эт3-75%, эт4-75%","▌Фасады НВФ. Монтаж керамогранита","эт2, эт3, эт4"]
[82,"▦ Витражи каркасы","Энсейв Констракшн",null,null,"▦ Витражи каркасы","эт1, эт2, эт3, эт4"]
[89,"Плитка стен в СУ"," ",null,null,"Плитка стен в СУ","эт1"]
[144,"ИТП жилых помещений"," ",null,null,"ИТП жилых помещений","Постав. обор."]
[149,"Мусоросборная камера"," ","Вх. дверь, ОВ ВК","Вх. дверь, ОВ ВК-0%","Мусоросборная камера","ОВ ВК"]
[151,"ГРЩ"," ","ЭО, СС","ЭО, СС","ГРЩ"]
["Секция 10"]
[15,"● Подвал. Лотки ЭО","ГПК Инжпетрострой (электрика)","подвал","подвал-90%","● Подвал. Лотки ЭО","подвал"]
[20,"Металлические решётки приямков в подвале","ГПК Инжпетрострой (металл)","подвал","подвал","Металлические решётки приямков в подвале"]
[21,"Металлические лестницы и ограждения в подвале","ГПК Инжпетрострой (металл)",null,null,"Металлические лестницы и ограждения в подвале","подвал"]
[23,"Подготовка монолита (шлифовка стен)","ЭнергоПроектСтрой","подвал","подвал-0%","Подготовка монолита (шлифовка стен)","подвал"]
[42,"▌Фасады на балконах. Окраска 1й слой","Арсенал Строй",null,null,"▌Фасады на балконах. Окраска 1й слой","эт1, эт2, эт3, эт4"]
[53,"▲ Кровля. Окрытие парапета","СК Интеп",null,null,"▲ Кровля. Окрытие парапета","кровля"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)","эт1, эт4","эт1, эт4-0%","Вмазка коробок и квартирных щитов","эт4"]
[69,"Клапаны ПД и ДУ","ТРАСТ","эт1, эт2, эт3, эт4","эт1, эт2, эт3, эт4","Клапаны ПД и ДУ"]
[71,"Двери технические и МОП","ССП Групп","подвал, эт1, эт2, эт3, эт4","подвал, эт1-0%, эт2-0%, эт3-0%, эт4-0%","Двери технические и МОП","эт1, эт2, эт3, эт4"]
[72,"Монтаж коллекторов","ТРАСТ","эт1, эт2, эт3, эт4","эт1, эт2, эт3, эт4","Монтаж коллекторов"]
[75,"▌Фасады с лесов. Декор","Арсенал Строй","эт2, эт3, эт4","эт2, эт3, эт4","▌Фасады с лесов. Декор"]
[76,"▌Фасады с лесов. Окраска","Арсенал Строй","кровля","кровля-0%","▌Фасады с лесов. Окраска","кровля"]
[77,"▌Фасады НВФ. Кронштейны","Арсенал Строй","эт1","эт1","▌Фасады НВФ. Кронштейны"]
[78,"▌Фасады НВФ. Утепление","Арсенал Строй","эт1","эт1","▌Фасады НВФ. Утепление"]
[79,"▌Фасады НВФ. Направляющие","Арсенал Строй","эт1","эт1-0%","▌Фасады НВФ. Направляющие","эт1"]
[80,"▌Фасады НВФ. Монтаж керамогранита","Арсенал Строй","эт2, эт3, эт4","эт2-0%, эт3-0%, эт4-0%","▌Фасады НВФ. Монтаж керамогранита","эт2, эт3, эт4"]
[89,"Плитка стен в СУ"," ",null,null,"Плитка стен в СУ","эт1"]
[149,"Мусоросборная камера"," ","Вх. дверь","Вх. дверь","Мусоросборная камера"]
["Секция 2"]
[20,"Металлические решётки приямков в подвале","ГПК Инжпетрострой (металл)","подвал","подвал","Металлические решётки приямков в подвале"]
[21,"Металлические лестницы и ограждения в подвале","ГПК Инжпетрострой (металл)","подвал","подвал","Металлические лестницы и ограждения в подвале"]
[23,"Подготовка монолита (шлифовка стен)","ЭнергоПроектСтрой","подвал","подвал-0%","Подготовка монолита (шлифовка стен)","подвал"]
[42,"▌Фасады на балконах. Окраска 1й слой","Арсенал Строй","эт1, эт2, эт3, эт4","эт1-10%, эт2-10%, эт3-10%, эт4-10%","▌Фасады на балконах. Окраска 1й слой","эт1, эт2, эт3, эт4"]
[52,"▲ Кровля. Гидроизоляция верхний слой","СК Интеп",null,null,"▲ Кровля. Гидроизоляция верхний слой","кровля"]
[53,"▲ Кровля. Окрытие парапета","СК Интеп","кровля","кровля-0%","▲ Кровля. Окрытие парапета","кровля"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)","эт3, эт4","эт3, эт4-0%","Вмазка коробок и квартирных щитов","эт4"]
[69,"Клапаны ПД и ДУ","ТРАСТ","эт2, эт3","эт2, эт3","Клапаны ПД и ДУ","эт4"]
[71,"Двери технические и МОП","ССП Групп","подвал, эт1, эт2, эт3, эт4","подвал, эт1-0%, эт2-0%, эт3-0%, эт4-0%","Двери технические и МОП","эт1, эт2, эт3, эт4"]
[72,"Монтаж коллекторов","ТРАСТ","эт2, эт3, эт4","эт2, эт3, эт4","Монтаж коллекторов"]
[76,"▌Фасады с лесов. Окраска","Арсенал Строй","кровля","кровля-0%","▌Фасады с лесов. Окраска","эт2, эт3, эт4, кровля"]
[77,"▌Фасады НВФ. Кронштейны","Арсенал Строй","эт1","эт1","▌Фасады НВФ. Кронштейны"]
[78,"▌Фасады НВФ. Утепление","Арсенал Строй","эт1","эт1","▌Фасады НВФ. Утепление"]
[79,"▌Фасады НВФ. Направляющие","Арсенал Строй","эт1","эт1-0%","▌Фасады НВФ. Направляющие","эт1"]
[80,"▌Фасады НВФ. Монтаж керамогранита","Арсенал Строй","эт2, эт3, эт4","эт2-75%, эт3-75%, эт4-75%","▌Фасады НВФ. Монтаж керамогранита","эт2, эт3, эт4"]
[82,"▦ Витражи каркасы","Энсейв Констракшн",null,null,"▦ Витражи каркасы","эт1, эт2, эт3, эт4"]
[89,"Плитка стен в СУ"," ",null,null,"Плитка стен в СУ","эт1"]
[145,"ИТП встройки"," ",null,null,"ИТП встройки","Постав. обор."]
[149,"Мусоросборная камера"," ","Вх. дверь, ОВ ВК","Вх. дверь, ОВ ВК-0%","Мусоросборная камера","ОВ ВК"]
["Секция 3"]
[15,"● Подвал. Лотки ЭО","ГПК Инжпетрострой (электрика)","подвал","подвал-90%","● Подвал. Лотки ЭО","подвал"]
[20,"Металлические решётки приямков в подвале","ГПК Инжпетрострой (металл)","подвал","подвал","Металлические решётки приямков в подвале"]
[21,"Металлические лестницы и ограждения в подвале","ГПК Инжпетрострой (металл)","подвал","подвал","Металлические лестницы и ограждения в подвале"]
[23,"Подготовка монолита (шлифовка стен)","ЭнергоПроектСтрой","подвал","подвал-0%","Подготовка монолита (шлифовка стен)","подвал"]
[42,"▌Фасады на балконах. Окраска 1й слой","Арсенал Строй","эт1, эт2, эт3, эт4","эт1-10%, эт2-10%, эт3-10%, эт4-10%","▌Фасады на балконах. Окраска 1й слой","эт1, эт2, эт3, эт4"]
[52,"▲ Кровля. Гидроизоляция верхний слой","СК Интеп",null,null,"▲ Кровля. Гидроизоляция верхний слой","кровля"]
[53,"▲ Кровля. Окрытие парапета","СК Интеп","кровля","кровля-0%","▲ Кровля. Окрытие парапета","кровля"]
[63,"Монтаж радиаторов","ТРАСТ","эт4","эт4","Монтаж радиаторов"]
[64,"Монтаж PEX","ТРАСТ","эт4","эт4","Монтаж PEX"]
[65,"Пневмоиспытания труб отопления","ТРАСТ","эт4","эт4","Пневмоиспытания труб отопления"]
[66,"Стяжка квартир и МОП","Ленстройгрупп","эт4","эт4","Стяжка квартир и МОП"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)","эт1, эт2, эт3, эт4","эт1, эт2, эт3-0%, эт4-0%","Вмазка коробок и квартирных щитов","эт3, эт4"]
[69,"Клапаны ПД и ДУ","ТРАСТ","эт1, эт2, эт3","эт1, эт2, эт3","Клапаны ПД и ДУ","эт4"]
[71,"Двери технические и МОП","ССП Групп","подвал, эт1, эт2, эт3, эт4","подвал, эт1-0%, эт2-0%, эт3-0%, эт4-0%","Двери технические и МОП","эт1, эт2, эт3, эт4"]
[72,"Монтаж коллекторов","ТРАСТ","эт2, эт3, эт4","эт2, эт3, эт4","Монтаж коллекторов"]
[76,"▌Фасады с лесов. Окраска","Арсенал Строй","кровля","кровля-0%","▌Фасады с лесов. Окраска","эт2, эт3, эт4, кровля"]
[79,"▌Фасады НВФ. Направляющие","Арсенал Строй","эт1","эт1-0%","▌Фасады НВФ. Направляющие","эт1"]
[80,"▌Фасады НВФ. Монтаж керамогранита","Арсенал Строй","эт2, эт3, эт4","эт2-75%, эт3-75%, эт4-75%","▌Фасады НВФ. Монтаж керамогранита","эт2, эт3, эт4"]
[82,"▦ Витражи каркасы","Энсейв Констракшн",null,null,"▦ Витражи каркасы","эт1, эт2, эт3, эт4"]
[89,"Плитка стен в СУ"," ",null,null,"Плитка стен в СУ","эт1"]
[146,"Водомерный узел"," ",null,null,"Водомерный узел","ОВ ВК, Постав. обор."]
[149,"Мусоросборная камера"," ","Вх. дверь, ОВ ВК","Вх. дверь, ОВ ВК-0%","Мусоросборная камера","ОВ ВК"]
["Секция 4"]
[15,"● Подвал. Лотки ЭО","ГПК Инжпетрострой (электрика)","подвал","подвал-90%","● Подвал. Лотки ЭО","подвал"]
[20,"Металлические решётки приямков в подвале","ГПК Инжпетрострой (металл)","подвал","подвал","Металлические решётки приямков в подвале"]
[21,"Металлические лестницы и ограждения в подвале","ГПК Инжпетрострой (металл)","подвал","подвал","Металлические лестницы и ограждения в подвале"]
[23,"Подготовка монолита (шлифовка стен)","ЭнергоПроектСтрой","подвал","подвал-0%","Подготовка монолита (шлифовка стен)","подвал"]
[42,"▌Фасады на балконах. Окраска 1й слой","Арсенал Строй","эт1, эт2, эт3, эт4","эт1-25%, эт2-25%, эт3-25%, эт4-25%","▌Фасады на балконах. Окраска 1й слой","эт1, эт2, эт3, эт4"]
[53,"▲ Кровля. Окрытие парапета","СК Интеп",null,null,"▲ Кровля. Окрытие парапета","кровля"]
[66,"Стяжка квартир и МОП","Ленстройгрупп","эт4","эт4-0%","Стяжка квартир и МОП","эт4"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)","эт1, эт4","эт1, эт4-0%","Вмазка коробок и квартирных щитов","эт4"]
[69,"Клапаны ПД и ДУ","ТРАСТ","эт1, эт2, эт3","эт1, эт2, эт3","Клапаны ПД и ДУ","эт4"]
[71,"Двери технические и МОП","ССП Групп","подвал, эт1, эт2, эт3, эт4","подвал, эт1-0%, эт2-0%, эт3-0%, эт4-0%","Двери технические и МОП","эт1, эт2, эт3, эт4"]
[72,"Монтаж коллекторов","ТРАСТ","эт1, эт2, эт3, эт4","эт1, эт2, эт3, эт4","Монтаж коллекторов"]
[73,"▌Фасады с лесов. Утепление","Арсенал Строй",null,null,"▌Фасады с лесов. Утепление","эт2, эт3, эт4"]
[74,"▌Фасады с лесов. Армировка","Арсенал Строй",null,null,"▌Фасады с лесов. Армировка","эт2, эт3, эт4"]
[76,"▌Фасады с лесов. Окраска","Арсенал Строй","кровля","кровля-0%","▌Фасады с лесов. Окраска","эт2, эт3, эт4, кровля"]
[79,"▌Фасады НВФ. Направляющие","Арсенал Строй","эт1","эт1-0%","▌Фасады НВФ. Направляющие","эт1"]
[80,"▌Фасады НВФ. Монтаж керамогранита","Арсенал Строй",null,null,"▌Фасады НВФ. Монтаж керамогранита","эт2, эт3, эт4"]
[89,"Плитка стен в СУ"," ",null,null,"Плитка стен в СУ","эт1"]
[149,"Мусоросборная камера"," ","Вх. дверь, ОВ ВК","Вх. дверь, ОВ ВК-0%","Мусоросборная камера","ОВ ВК"]
["Секция 5"]
[20,"Металлические решётки приямков в подвале","ГПК Инжпетрострой (металл)","подвал","подвал","Металлические решётки приямков в подвале"]
[21,"Металлические лестницы и ограждения в подвале","ГПК Инжпетрострой (металл)","подвал","подвал-0%","Металлические лестницы и ограждения в подвале","подвал"]
[23,"Подготовка монолита (шлифовка стен)","ЭнергоПроектСтрой","подвал","подвал-0%","Подготовка монолита (шлифовка стен)","подвал"]
[42,"▌Фасады на балконах. Окраска 1й слой","Арсенал Строй","эт1, эт2, эт3, эт4","эт1-25%, эт2-25%, эт3-25%, эт4-25%","▌Фасады на балконах. Окраска 1й слой","эт1, эт2, эт3, эт4"]
[53,"▲ Кровля. Окрытие парапета","СК Интеп",null,null,"▲ Кровля. Окрытие парапета","кровля"]
[61,"✱ Штукатурка стен вкруг и потолков","СТР","эт3","эт3-0%","✱ Штукатурка стен вкруг и потолков","эт3, эт4"]
[62,"Монтаж подложки под PEX","СТР","эт2, эт3","эт2-0%, эт3-0%","Монтаж подложки под PEX","эт2, эт3, эт4"]
[63,"Монтаж радиаторов","ТРАСТ","эт2, эт3","эт2-0%, эт3-0%","Монтаж радиаторов","эт2, эт3, эт4"]
[64,"Монтаж PEX","ТРАСТ","эт2, эт3","эт2-0%, эт3-0%","Монтаж PEX","эт2, эт3, эт4"]
[65,"Пневмоиспытания труб отопления","ТРАСТ","эт2, эт3","эт2-0%, эт3-0%","Пневмоиспытания труб отопления","эт2, эт3, эт4"]
[66,"Стяжка квартир и МОП","СТР","эт1, эт2","эт1-0%, эт2-0%","Стяжка квартир и МОП","эт1, эт2, эт3"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)","эт1","эт1-0%","Вмазка коробок и квартирных щитов","эт1, эт3"]
[69,"Клапаны ПД и ДУ","ТРАСТ",null,null,"Клапаны ПД и ДУ","эт1, эт3"]
[70,"Штукатурка лестниц","СТР",null,null,"Штукатурка лестниц","эт1, эт2, эт3, эт4"]
[71,"Двери технические и МОП","ССП Групп","подвал, эт1","подвал, эт1-0%","Двери технические и МОП","эт1, эт3"]
[72,"Монтаж коллекторов","ТРАСТ",null,null,"Монтаж коллекторов","эт1, эт2, эт3"]
[76,"▌Фасады с лесов. Окраска","Арсенал Строй","кровля","кровля-0%","▌Фасады с лесов. Окраска","кровля"]
[79,"▌Фасады НВФ. Направляющие","Арсенал Строй","эт1","эт1-0%","▌Фасады НВФ. Направляющие","эт1"]
[80,"▌Фасады НВФ. Монтаж керамогранита","Арсенал Строй",null,null,"▌Фасады НВФ. Монтаж керамогранита","эт2, эт3, эт4"]
[89,"Плитка стен в СУ"," ",null,null,"Плитка стен в СУ","эт1"]
[149,"Мусоросборная камера"," ","Черн. отд., Вх. дверь, Чист. отд., ОВ ВК","Черн. отд.-0%, Вх. дверь, Чист. отд.-0%, ОВ ВК-0%","Мусоросборная камера","Черн. отд., Чист. отд., ОВ ВК"]
["Секция 6"]
[20,"Металлические решётки приямков в подвале","ГПК Инжпетрострой (металл)","подвал","подвал","Металлические решётки приямков в подвале"]
[21,"Металлические лестницы и ограждения в подвале","ГПК Инжпетрострой (металл)","подвал","подвал-0%","Металлические лестницы и ограждения в подвале","подвал"]
[23,"Подготовка монолита (шлифовка стен)","ЭнергоПроектСтрой","подвал","подвал-0%","Подготовка монолита (шлифовка стен)","подвал"]
[42,"▌Фасады на балконах. Окраска 1й слой","Арсенал Строй","эт1, эт2, эт3, эт4","эт1-25%, эт2-25%, эт3-25%, эт4-25%","▌Фасады на балконах. Окраска 1й слой","эт1, эт2, эт3, эт4"]
[52,"▲ Кровля. Гидроизоляция верхний слой","СК Интеп",null,null,"▲ Кровля. Гидроизоляция верхний слой","кровля"]
[53,"▲ Кровля. Окрытие парапета","СК Интеп","кровля","кровля-0%","▲ Кровля. Окрытие парапета","кровля"]
[61,"✱ Штукатурка стен вкруг и потолков","СТР","эт2, эт3","эт2-90%, эт3-0%","✱ Штукатурка стен вкруг и потолков","эт2, эт3, эт4"]
[62,"Монтаж подложки под PEX","СТР","эт2, эт3","эт2-0%, эт3-0%","Монтаж подложки под PEX","эт2, эт3, эт4"]
[63,"Монтаж радиаторов","ТРАСТ","эт2","эт2-0%","Монтаж радиаторов","эт2, эт3"]
[64,"Монтаж PEX","ТРАСТ","эт2","эт2-0%","Монтаж PEX","эт2, эт3"]
[65,"Пневмоиспытания труб отопления","ТРАСТ","эт2","эт2-0%","Пневмоиспытания труб отопления","эт2, эт3"]
[66,"Стяжка квартир и МОП","СТР","эт1, эт2","эт1-0%, эт2-0%","Стяжка квартир и МОП","эт1, эт2, эт3"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)","эт1","эт1-0%","Вмазка коробок и квартирных щитов","эт1, эт2"]
[69,"Клапаны ПД и ДУ","ТРАСТ",null,null,"Клапаны ПД и ДУ","эт1, эт2"]
[71,"Двери технические и МОП","ССП Групп","подвал, эт1, эт2","подвал, эт1, эт2-0%","Двери технические и МОП","эт2, эт3"]
[72,"Монтаж коллекторов","ТРАСТ",null,null,"Монтаж коллекторов","эт1, эт2"]
[76,"▌Фасады с лесов. Окраска","Арсенал Строй","кровля","кровля-0%","▌Фасады с лесов. Окраска","эт2, эт3, эт4, кровля"]
[79,"▌Фасады НВФ. Направляющие","Арсенал Строй","эт1","эт1-0%","▌Фасады НВФ. Направляющие","эт1"]
[80,"▌Фасады НВФ. Монтаж керамогранита","Арсенал Строй","эт2, эт3, эт4","эт2-0%, эт3-0%, эт4-0%","▌Фасады НВФ. Монтаж керамогранита","эт2, эт3, эт4"]
[82,"▦ Витражи каркасы","Энсейв Констракшн",null,null,"▦ Витражи каркасы","эт1, эт2, эт3, эт4"]
[89,"Плитка стен в СУ"," ",null,null,"Плитка стен в СУ","эт1"]
[149,"Мусоросборная камера"," ","Черн. отд., Вх. дверь, Чист. отд., ОВ ВК","Черн. отд.-0%, Вх. дверь, Чист. отд.-0%, ОВ ВК-0%","Мусоросборная камера","Черн. отд., Чист. отд., ОВ ВК"]
[151,"ГРЩ"," ","Черн. отд., Вх. дверь, Чист. отд., ЭО, СС","Черн. отд.-0%, Вх. дверь-0%, Чист. отд.-0%, ЭО-0%, СС-0%","ГРЩ","Черн. отд., Вх. дверь, Чист. отд., ЭО, СС"]
["Секция 7"]
[20,"Металлические решётки приямков в подвале","ГПК Инжпетрострой (металл)","подвал","подвал","Металлические решётки приямков в подвале"]
[21,"Металлические лестницы и ограждения в подвале","ГПК Инжпетрострой (металл)","подвал","подвал-0%","Металлические лестницы и ограждения в подвале","подвал"]
[23,"Подготовка монолита (шлифовка стен)","ЭнергоПроектСтрой","подвал","подвал-0%","Подготовка монолита (шлифовка стен)","подвал"]
[42,"▌Фасады на балконах. Окраска 1й слой","Арсенал Строй","эт1, эт2, эт3, эт4","эт1-25%, эт2-25%, эт3-25%, эт4-25%","▌Фасады на балконах. Окраска 1й слой","эт1, эт2, эт3, эт4"]
[52,"▲ Кровля. Гидроизоляция верхний слой","СК Интеп",null,null,"▲ Кровля. Гидроизоляция верхний слой","кровля"]
[53,"▲ Кровля. Окрытие парапета","СК Интеп","кровля","кровля-0%","▲ Кровля. Окрытие парапета","кровля"]
[63,"Монтаж радиаторов","ТРАСТ","эт4","эт4","Монтаж радиаторов"]
[64,"Монтаж PEX","ТРАСТ","эт4","эт4","Монтаж PEX"]
[65,"Пневмоиспытания труб отопления","ТРАСТ","эт4","эт4","Пневмоиспытания труб отопления"]
[66,"Стяжка квартир и МОП","СТР","эт4","эт4-0%","Стяжка квартир и МОП","эт4"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)","эт1, эт2, эт3, эт4","эт1, эт2-0%, эт3-0%, эт4-0%","Вмазка коробок и квартирных щитов","эт2, эт3, эт4"]
[69,"Клапаны ПД и ДУ","ТРАСТ","эт1, эт2, эт3","эт1, эт2, эт3","Клапаны ПД и ДУ","эт4"]
[71,"Двери технические и МОП","ССП Групп","подвал, эт1, эт2, эт3, эт4","подвал, эт1-0%, эт2-0%, эт3-0%, эт4-0%","Двери технические и МОП","эт1, эт2, эт3, эт4"]
[72,"Монтаж коллекторов","ТРАСТ","эт1, эт2, эт4","эт1, эт2, эт4","Монтаж коллекторов","эт3"]
[76,"▌Фасады с лесов. Окраска","Арсенал Строй","кровля","кровля-0%","▌Фасады с лесов. Окраска","эт2, эт3, эт4, кровля"]
[79,"▌Фасады НВФ. Направляющие","Арсенал Строй","эт1","эт1-0%","▌Фасады НВФ. Направляющие","эт1"]
[80,"▌Фасады НВФ. Монтаж керамогранита","Арсенал Строй","эт2, эт3, эт4","эт2-0%, эт3-0%, эт4-0%","▌Фасады НВФ. Монтаж керамогранита","эт2, эт3, эт4"]
[82,"▦ Витражи каркасы","Энсейв Констракшн","эт1, эт2, эт3, эт4","эт1-0%, эт2-0%, эт3-0%, эт4-0%","▦ Витражи каркасы","эт1, эт2, эт3, эт4"]
[89,"Плитка стен в СУ"," ",null,null,"Плитка стен в СУ","эт1"]
[149,"Мусоросборная камера"," ","Черн. отд., Вх. дверь, Чист. отд., ОВ ВК","Черн. отд.-0%, Вх. дверь, Чист. отд.-0%, ОВ ВК-0%","Мусоросборная камера","Черн. отд., Чист. отд., ОВ ВК"]
["Секция 8"]
[20,"Металлические решётки приямков в подвале","ГПК Инжпетрострой (металл)","подвал","подвал","Металлические решётки приямков в подвале"]
[21,"Металлические лестницы и ограждения в подвале","ГПК Инжпетрострой (металл)","подвал","подвал-0%","Металлические лестницы и ограждения в подвале","подвал"]
[23,"Подготовка монолита (шлифовка стен)","ЭнергоПроектСтрой","подвал","подвал-0%","Подготовка монолита (шлифовка стен)","подвал"]
[42,"▌Фасады на балконах. Окраска 1й слой","Арсенал Строй",null,null,"▌Фасады на балконах. Окраска 1й слой","эт1, эт2, эт3, эт4"]
[52,"▲ Кровля. Гидроизоляция верхний слой","СК Интеп",null,null,"▲ Кровля. Гидроизоляция верхний слой","кровля"]
[53,"▲ Кровля. Окрытие парапета","СК Интеп","кровля","кровля-0%","▲ Кровля. Окрытие парапета","кровля"]
[71,"Двери технические и МОП","ССП Групп","подвал, эт1, эт2, эт3, эт4","подвал, эт1, эт2, эт3, эт4","Двери технические и МОП"]
[76,"▌Фасады с лесов. Окраска","Арсенал Строй","кровля","кровля-0%","▌Фасады с лесов. Окраска","эт2, эт3, эт4, кровля"]
[77,"▌Фасады НВФ. Кронштейны","Арсенал Строй","эт1","эт1","▌Фасады НВФ. Кронштейны"]
[78,"▌Фасады НВФ. Утепление","Арсенал Строй","эт1","эт1","▌Фасады НВФ. Утепление"]
[79,"▌Фасады НВФ. Направляющие","Арсенал Строй","эт1","эт1-0%","▌Фасады НВФ. Направляющие","эт1"]
[80,"▌Фасады НВФ. Монтаж керамогранита","Арсенал Строй","эт2, эт3, эт4","эт2-0%, эт3-0%, эт4-0%","▌Фасады НВФ. Монтаж керамогранита","эт2, эт3, эт4"]
[82,"▦ Витражи каркасы","Энсейв Констракшн",null,null,"▦ Витражи каркасы","эт1, эт2, эт3, эт4"]
[89,"Плитка стен в СУ"," ",null,null,"Плитка стен в СУ","эт1"]
[149,"Мусоросборная камера"," ","Черн. отд., Вх. дверь, Чист. отд., ОВ ВК","Черн. отд.-0%, Вх. дверь, Чист. отд.-0%, ОВ ВК-0%","Мусоросборная камера","Черн. отд., Чист. отд., ОВ ВК"]
["Секция 9"]
[20,"Металлические решётки приямков в подвале","ГПК Инжпетрострой (металл)","подвал","подвал","Металлические решётки приямков в подвале"]
[21,"Металлические лестницы и ограждения в подвале","ГПК Инжпетрострой (металл)",null,null,"Металлические лестницы и ограждения в подвале","подвал"]
[23,"Подготовка монолита (шлифовка стен)","ЭнергоПроектСтрой","подвал","подвал-0%","Подготовка монолита (шлифовка стен)","подвал"]
[42,"▌Фасады на балконах. Окраска 1й слой","Арсенал Строй",null,null,"▌Фасады на балконах. Окраска 1й слой","эт1, эт2, эт3, эт4"]
[53,"▲ Кровля. Окрытие парапета","СК Интеп",null,null,"▲ Кровля. Окрытие парапета","кровля"]
[61,"✱ Штукатурка стен вкруг и потолков","СТР","эт2, эт3","эт2-90%, эт3-0%","✱ Штукатурка стен вкруг и потолков","эт2, эт3, эт4"]
[62,"Монтаж подложки под PEX","СТР","эт2, эт3","эт2-0%, эт3-0%","Монтаж подложки под PEX","эт2, эт3, эт4"]
[63,"Монтаж радиаторов","ТРАСТ","эт2, эт3","эт2-0%, эт3-0%","Монтаж радиаторов","эт2, эт3, эт4"]
[64,"Монтаж PEX","ТРАСТ","эт2, эт3","эт2-0%, эт3-0%","Монтаж PEX","эт2, эт3, эт4"]
[65,"Пневмоиспытания труб отопления","ТРАСТ","эт2, эт3","эт2-0%, эт3-0%","Пневмоиспытания труб отопления","эт2, эт3, эт4"]
[66,"Стяжка квартир и МОП","СТР","эт1","эт1-0%","Стяжка квартир и МОП","эт1, эт2, эт3"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)",null,null,"Вмазка коробок и квартирных щитов","эт1, эт2"]
[69,"Клапаны ПД и ДУ","ТРАСТ",null,null,"Клапаны ПД и ДУ","эт1, эт2"]
[70,"Штукатурка лестниц","СТР",null,null,"Штукатурка лестниц","эт1, эт2, эт3, эт4"]
[71,"Двери технические и МОП","ССП Групп","подвал, эт1","подвал, эт1-0%","Двери технические и МОП","эт1, эт2, эт3"]
[72,"Монтаж коллекторов","ТРАСТ",null,null,"Монтаж коллекторов","эт1, эт2"]
[76,"▌Фасады с лесов. Окраска","Арсенал Строй","кровля","кровля-0%","▌Фасады с лесов. Окраска","кровля"]
[77,"▌Фасады НВФ. Кронштейны","Арсенал Строй","эт1","эт1","▌Фасады НВФ. Кронштейны"]
[78,"▌Фасады НВФ. Утепление","Арсенал Строй","эт1","эт1","▌Фасады НВФ. Утепление"]
[79,"▌Фасады НВФ. Направляющие","Арсенал Строй","эт1","эт1-0%","▌Фасады НВФ. Направляющие","эт1"]
[80,"▌Фасады НВФ. Монтаж керамогранита","Арсенал Строй","эт2, эт3, эт4","эт2-0%, эт3-0%, эт4-0%","▌Фасады НВФ. Монтаж керамогранита","эт2, эт3, эт4"]
[82,"▦ Витражи каркасы","Энсейв Констракшн","эт1, эт2, эт3, эт4","эт1-0%, эт2-0%, эт3-0%, эт4-0%","▦ Витражи каркасы","эт1, эт2, эт3, эт4"]
[89,"Плитка стен в СУ"," ",null,null,"Плитка стен в СУ","эт1"]
[149,"Мусоросборная камера"," ","Черн. отд., Вх. дверь, Чист. отд., ОВ ВК","Черн. отд.-0%, Вх. дверь, Чист. отд.-0%, ОВ ВК-0%","Мусоросборная камера","Черн. отд., Чист. отд., ОВ ВК"]
["НС-3. Резиденции. Уч. 26 / 6-я оч. / Корпус 6.2"]
["Секция 1"]
[19,"● Подвал. Трубопровод системы отопления","СК ИнжСтрой",null,null,"● Подвал. Трубопровод системы отопления","подвал"]
[61,"✱ Штукатурка стен вкруг и потолков","Фаст Компани","эт4","эт4","✱ Штукатурка стен вкруг и потолков"]
[62,"Монтаж подложки под PEX","Фаст Компани","эт3, эт4","эт3, эт4","Монтаж подложки под PEX"]
[63,"Монтаж радиаторов","СК ИнжСтрой","эт3","эт3-0%","Монтаж радиаторов","эт3, эт4"]
[64,"Монтаж PEX","СК ИнжСтрой","эт3","эт3-0%","Монтаж PEX","эт3, эт4"]
[65,"Пневмоиспытания труб отопления","СК ИнжСтрой","эт3","эт3-0%","Пневмоиспытания труб отопления","эт3, эт4"]
[66,"Стяжка квартир и МОП","Фаст Компани","эт2, эт3","эт2, эт3-0%","Стяжка квартир и МОП","эт3, эт4"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)","эт1, эт2","эт1, эт2","Вмазка коробок и квартирных щитов","эт3"]
[68,"Этажные щиты ЭО и СС в МОП","ГПК Инжпетрострой (электрика)","эт1, эт2","эт1-0%, эт2-0%","Этажные щиты ЭО и СС в МОП","эт1, эт2, эт3, эт4"]
[69,"Клапаны ПД и ДУ","СК ИнжСтрой","эт1, эт2, эт3","эт1, эт2, эт3-0%","Клапаны ПД и ДУ","эт3, эт4"]
[70,"Штукатурка лестниц","Фаст Компани","эт1, эт2, эт3, эт4","эт1, эт2, эт3, эт4","Штукатурка лестниц"]
[72,"Монтаж коллекторов","СК ИнжСтрой","эт1, эт2","эт1, эт2","Монтаж коллекторов"]
[149,"Мусоросборная камера"," ","Черн. отд., Вх. дверь, ОВ ВК","Черн. отд.-0%, Вх. дверь-0%, ОВ ВК-0%","Мусоросборная камера","Черн. отд., Вх. дверь, Чист. отд., ОВ ВК"]
[151,"ГРЩ"," ","Черн. отд., Вх. дверь, ЭО, СС, Постав. обор.","Черн. отд.-0%, Вх. дверь-0%, ЭО-0%, СС-0%, Постав. обор.-0%","ГРЩ","Черн. отд., Вх. дверь, Чист. отд., ЭО, СС, Постав. обор."]
["Секция 10"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)","эт4","эт4","Вмазка коробок и квартирных щитов"]
[68,"Этажные щиты ЭО и СС в МОП","ГПК Инжпетрострой (электрика)","эт1, эт2","эт1-0%, эт2-0%","Этажные щиты ЭО и СС в МОП","эт1, эт2"]
[71,"Двери технические и МОП","ТОУН СПб",null,null,"Двери технические и МОП","эт1"]
[72,"Монтаж коллекторов","СК ИнжСтрой","эт1, эт2, эт3","эт1, эт2, эт3","Монтаж коллекторов","эт4"]
[73,"▌Фасады с лесов. Утепление","СУ Эдельвейс","эт2, эт3, эт4","эт2-0%, эт3-0%, эт4-0%","▌Фасады с лесов. Утепление","эт2, эт3, эт4"]
[74,"▌Фасады с лесов. Армировка","СУ Эдельвейс",null,null,"▌Фасады с лесов. Армировка","эт2, эт3, эт4"]
[149,"Мусоросборная камера"," ",null,null,"Мусоросборная камера","Черн. отд., ОВ ВК"]
["Секция 2"]
[61,"✱ Штукатурка стен вкруг и потолков","Фаст Компани","эт3","эт3","✱ Штукатурка стен вкруг и потолков","эт4"]
[62,"Монтаж подложки под PEX","Фаст Компани","эт3","эт3","Монтаж подложки под PEX","эт4"]
[63,"Монтаж радиаторов","СК ИнжСтрой",null,null,"Монтаж радиаторов","эт3, эт4"]
[64,"Монтаж PEX","СК ИнжСтрой",null,null,"Монтаж PEX","эт3"]
[65,"Пневмоиспытания труб отопления","СК ИнжСтрой","эт2","эт2","Пневмоиспытания труб отопления","эт3"]
[66,"Стяжка квартир и МОП","Фаст Компани","эт2","эт2","Стяжка квартир и МОП","эт3"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)",null,null,"Вмазка коробок и квартирных щитов","эт2, эт3"]
[68,"Этажные щиты ЭО и СС в МОП","ГПК Инжпетрострой (электрика)","эт2","эт2-0%","Этажные щиты ЭО и СС в МОП","эт2, эт3"]
[69,"Клапаны ПД и ДУ","СК ИнжСтрой","эт2","эт2-0%","Клапаны ПД и ДУ","эт2, эт3"]
[70,"Штукатурка лестниц","Фаст Компани",null,null,"Штукатурка лестниц","эт1, эт2, эт3, эт4"]
[71,"Двери технические и МОП","ТОУН СПб","подвал","подвал","Двери технические и МОП"]
[72,"Монтаж коллекторов","СК ИнжСтрой","эт2","эт2","Монтаж коллекторов","эт3"]
[73,"▌Фасады с лесов. Утепление","СУ Эдельвейс","эт2, эт3, эт4","эт2-50%, эт3-50%, эт4-50%","▌Фасады с лесов. Утепление","эт2, эт3, эт4"]
[74,"▌Фасады с лесов. Армировка","СУ Эдельвейс","эт2, эт3, эт4","эт2-50%, эт3-50%, эт4-50%","▌Фасады с лесов. Армировка","эт2, эт3, эт4"]
[75,"▌Фасады с лесов. Декор","СУ Эдельвейс",null,null,"▌Фасады с лесов. Декор","эт2, эт3, эт4"]
[149,"Мусоросборная камера"," ","Черн. отд., Вх. дверь","Черн. отд.-0%, Вх. дверь-0%","Мусоросборная камера","Черн. отд., Вх. дверь, Чист. отд., ОВ ВК"]
["Секция 3"]
[62,"Монтаж подложки под PEX","Фаст Компани",null,null,"Монтаж подложки под PEX","эт4"]
[63,"Монтаж радиаторов","СК ИнжСтрой",null,null,"Монтаж радиаторов","эт4"]
[64,"Монтаж PEX","СК ИнжСтрой",null,null,"Монтаж PEX","эт4"]
[65,"Пневмоиспытания труб отопления","СК ИнжСтрой","эт3","эт3","Пневмоиспытания труб отопления","эт4"]
[66,"Стяжка квартир и МОП","Фаст Компани",null,null,"Стяжка квартир и МОП","эт3"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)",null,null,"Вмазка коробок и квартирных щитов","эт3"]
[68,"Этажные щиты ЭО и СС в МОП","ГПК Инжпетрострой (электрика)","эт2, эт3","эт2, эт3","Этажные щиты ЭО и СС в МОП"]
[70,"Штукатурка лестниц","Фаст Компани",null,null,"Штукатурка лестниц","эт1, эт2, эт3, эт4"]
[71,"Двери технические и МОП","ТОУН СПб","подвал","подвал-0%","Двери технические и МОП","подвал"]
[72,"Монтаж коллекторов","СК ИнжСтрой","эт2, эт3","эт2, эт3","Монтаж коллекторов"]
[73,"▌Фасады с лесов. Утепление","СУ Эдельвейс","эт2, эт3, эт4","эт2-50%, эт3-50%, эт4-50%","▌Фасады с лесов. Утепление","эт2, эт3, эт4"]
[74,"▌Фасады с лесов. Армировка","СУ Эдельвейс","эт2, эт3, эт4","эт2-50%, эт3-50%, эт4-50%","▌Фасады с лесов. Армировка","эт2, эт3, эт4"]
[75,"▌Фасады с лесов. Декор","СУ Эдельвейс",null,null,"▌Фасады с лесов. Декор","эт2, эт3, эт4"]
[149,"Мусоросборная камера"," ","Черн. отд., Вх. дверь","Черн. отд.-0%, Вх. дверь-0%","Мусоросборная камера","Черн. отд., Вх. дверь, Чист. отд., ОВ ВК"]
["Секция 4"]
[61,"✱ Штукатурка стен вкруг и потолков","Фаст Компани","эт2","эт2","✱ Штукатурка стен вкруг и потолков","эт3"]
[62,"Монтаж подложки под PEX","Фаст Компани","эт2","эт2","Монтаж подложки под PEX","эт3"]
[63,"Монтаж радиаторов","СК ИнжСтрой",null,null,"Монтаж радиаторов","эт2, эт3"]
[64,"Монтаж PEX","СК ИнжСтрой",null,null,"Монтаж PEX","эт2, эт3"]
[65,"Пневмоиспытания труб отопления","СК ИнжСтрой",null,null,"Пневмоиспытания труб отопления","эт2, эт3"]
[66,"Стяжка квартир и МОП","Фаст Компани",null,null,"Стяжка квартир и МОП","эт2"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)",null,null,"Вмазка коробок и квартирных щитов","эт2"]
[68,"Этажные щиты ЭО и СС в МОП","ГПК Инжпетрострой (электрика)",null,null,"Этажные щиты ЭО и СС в МОП","эт2"]
[69,"Клапаны ПД и ДУ","СК ИнжСтрой",null,null,"Клапаны ПД и ДУ","эт2"]
[71,"Двери технические и МОП","ТОУН СПб","подвал","подвал-0%","Двери технические и МОП","подвал"]
[72,"Монтаж коллекторов","СК ИнжСтрой",null,null,"Монтаж коллекторов","эт2"]
[74,"▌Фасады с лесов. Армировка","СУ Эдельвейс","эт2, эт3, эт4","эт2-0%, эт3-0%, эт4-0%","▌Фасады с лесов. Армировка","эт2, эт3, эт4"]
[75,"▌Фасады с лесов. Декор","СУ Эдельвейс",null,null,"▌Фасады с лесов. Декор","эт2, эт3, эт4"]
[77,"▌Фасады НВФ. Кронштейны","СУ Эдельвейс","эт2, эт3, эт4","эт2, эт3, эт4","▌Фасады НВФ. Кронштейны"]
[78,"▌Фасады НВФ. Утепление","СУ Эдельвейс","эт2, эт3, эт4","эт2-0%, эт3-0%, эт4-0%","▌Фасады НВФ. Утепление","эт2, эт3, эт4"]
[79,"▌Фасады НВФ. Направляющие","СУ Эдельвейс",null,null,"▌Фасады НВФ. Направляющие","эт2, эт3, эт4"]
[144,"ИТП жилых помещений"," ","Вх. дверь","Вх. дверь-0%","ИТП жилых помещений","Вх. дверь, Постав. обор."]
[145,"ИТП встройки"," ","Вх. дверь","Вх. дверь-0%","ИТП встройки","Вх. дверь, Постав. обор."]
[149,"Мусоросборная камера"," ",null,null,"Мусоросборная камера","Черн. отд., ОВ ВК"]
["Секция 5"]
[71,"Двери технические и МОП","ТОУН СПб","подвал","подвал","Двери технические и МОП"]
[72,"Монтаж коллекторов","СК ИнжСтрой","эт2, эт4","эт2, эт4","Монтаж коллекторов"]
[73,"▌Фасады с лесов. Утепление","СУ Эдельвейс","эт2, эт3, эт4","эт2-50%, эт3-50%, эт4-50%","▌Фасады с лесов. Утепление","эт2, эт3, эт4"]
[74,"▌Фасады с лесов. Армировка","СУ Эдельвейс",null,null,"▌Фасады с лесов. Армировка","эт2, эт3, эт4"]
[77,"▌Фасады НВФ. Кронштейны","СУ Эдельвейс","эт2, эт3, эт4","эт2, эт3, эт4","▌Фасады НВФ. Кронштейны"]
[78,"▌Фасады НВФ. Утепление","СУ Эдельвейс","эт2, эт3, эт4","эт2-0%, эт3-0%, эт4-0%","▌Фасады НВФ. Утепление","эт2, эт3, эт4"]
[79,"▌Фасады НВФ. Направляющие","СУ Эдельвейс",null,null,"▌Фасады НВФ. Направляющие","эт2, эт3, эт4"]
[149,"Мусоросборная камера"," ","Черн. отд., ОВ ВК","Черн. отд.-0%, ОВ ВК-0%","Мусоросборная камера","Черн. отд., Чист. отд., ОВ ВК"]
["Секция 6"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)","эт2, эт3, эт4","эт2, эт3-0%, эт4-0%","Вмазка коробок и квартирных щитов","эт3, эт4"]
[71,"Двери технические и МОП","ТОУН СПб","подвал","подвал-0%","Двери технические и МОП","подвал"]
[72,"Монтаж коллекторов","СК ИнжСтрой","эт4","эт4","Монтаж коллекторов"]
[73,"▌Фасады с лесов. Утепление","СУ Эдельвейс","эт2, эт3, эт4","эт2-50%, эт3-50%, эт4-50%","▌Фасады с лесов. Утепление","эт2, эт3, эт4"]
[74,"▌Фасады с лесов. Армировка","СУ Эдельвейс",null,null,"▌Фасады с лесов. Армировка","эт2, эт3, эт4"]
[77,"▌Фасады НВФ. Кронштейны","СУ Эдельвейс",null,null,"▌Фасады НВФ. Кронштейны","эт2, эт3, эт4"]
[78,"▌Фасады НВФ. Утепление","СУ Эдельвейс",null,null,"▌Фасады НВФ. Утепление","эт2, эт3, эт4"]
[82,"▦ Витражи каркасы","Энсейв Констракшн",null,null,"▦ Витражи каркасы","эт2, эт3, эт4"]
[146,"Водомерный узел"," ","Черн. отд., Вх. дверь","Черн. отд.-0%, Вх. дверь-0%","Водомерный узел","Черн. отд., Вх. дверь, Чист. отд., ЭО, СС"]
[149,"Мусоросборная камера"," ","Черн. отд.","Черн. отд.-0%","Мусоросборная камера","Черн. отд., Чист. отд., ОВ ВК"]
[150,"Помещение уборочного инвентаря"," ","Черн. отд., Вх. дверь","Черн. отд., Вх. дверь-0%","Помещение уборочного инвентаря","Вх. дверь, Чист. отд., ОВ ВК, ЭО, СС"]
[151,"ГРЩ"," ","Черн. отд., Вх. дверь, Чист. отд., ЭО, СС, Постав. обор.","Черн. отд., Вх. дверь-0%, Чист. отд.-0%, ЭО-0%, СС-0%, Постав. обор.-0%","ГРЩ","Вх. дверь, Чист. отд., ЭО, СС, Постав. обор."]
["Секция 7"]
[62,"Монтаж подложки под PEX","Гарант Строй Сервис","эт3, эт4","эт3, эт4","Монтаж подложки под PEX"]
[63,"Монтаж радиаторов","СК ИнжСтрой","эт3, эт4","эт3-0%, эт4-0%","Монтаж радиаторов","эт3, эт4"]
[64,"Монтаж PEX","СК ИнжСтрой","эт3, эт4","эт3-0%, эт4-0%","Монтаж PEX","эт3, эт4"]
[65,"Пневмоиспытания труб отопления","СК ИнжСтрой","эт3, эт4","эт3-0%, эт4-0%","Пневмоиспытания труб отопления","эт3, эт4"]
[66,"Стяжка квартир и МОП","Гарант Строй Сервис","эт3, эт4","эт3-0%, эт4-0%","Стяжка квартир и МОП","эт3, эт4"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)","эт1, эт2, эт3","эт1-0%, эт2-0%, эт3-0%","Вмазка коробок и квартирных щитов","эт1, эт2, эт3, эт4"]
[68,"Этажные щиты ЭО и СС в МОП","ГПК Инжпетрострой (электрика)","эт1, эт2, эт3","эт1-0%, эт2-0%, эт3-0%","Этажные щиты ЭО и СС в МОП","эт1, эт2, эт3, эт4"]
[69,"Клапаны ПД и ДУ","СК ИнжСтрой","эт3, эт4","эт3-0%, эт4-0%","Клапаны ПД и ДУ","эт3, эт4"]
[71,"Двери технические и МОП","ТОУН СПб","подвал","подвал","Двери технические и МОП","эт1"]
[72,"Монтаж коллекторов","СК ИнжСтрой","эт1, эт2, эт3, эт4","эт1, эт2, эт3, эт4","Монтаж коллекторов"]
[73,"▌Фасады с лесов. Утепление","СУ Эдельвейс","эт2, эт3, эт4","эт2-50%, эт3-50%, эт4-50%","▌Фасады с лесов. Утепление","эт2, эт3, эт4"]
[74,"▌Фасады с лесов. Армировка","СУ Эдельвейс",null,null,"▌Фасады с лесов. Армировка","эт2, эт3, эт4"]
[149,"Мусоросборная камера"," ","Черн. отд.","Черн. отд.-0%","Мусоросборная камера","Черн. отд., Чист. отд., ОВ ВК"]
["Секция 8"]
[61,"✱ Штукатурка стен вкруг и потолков","Гарант Строй Сервис","эт3","эт3","✱ Штукатурка стен вкруг и потолков"]
[62,"Монтаж подложки под PEX","Гарант Строй Сервис","эт1, эт2, эт3","эт1, эт2, эт3","Монтаж подложки под PEX","эт4"]
[63,"Монтаж радиаторов","СК ИнжСтрой","эт1, эт2","эт1-0%, эт2-0%","Монтаж радиаторов","эт1, эт2, эт3, эт4"]
[64,"Монтаж PEX","СК ИнжСтрой","эт1, эт2","эт1-0%, эт2-0%","Монтаж PEX","эт1, эт2, эт3, эт4"]
[65,"Пневмоиспытания труб отопления","СК ИнжСтрой","эт1, эт2","эт1-0%, эт2-0%","Пневмоиспытания труб отопления","эт1, эт2, эт3, эт4"]
[66,"Стяжка квартир и МОП","Гарант Строй Сервис","эт1, эт2","эт1-0%, эт2-0%","Стяжка квартир и МОП","эт1, эт2, эт3"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)",null,null,"Вмазка коробок и квартирных щитов","эт1, эт2"]
[68,"Этажные щиты ЭО и СС в МОП","ГПК Инжпетрострой (электрика)","эт1","эт1","Этажные щиты ЭО и СС в МОП","эт2, эт3"]
[69,"Клапаны ПД и ДУ","СК ИнжСтрой","эт1, эт2","эт1-0%, эт2-0%","Клапаны ПД и ДУ","эт1, эт2, эт3"]
[71,"Двери технические и МОП","ТОУН СПб","подвал","подвал","Двери технические и МОП"]
[73,"▌Фасады с лесов. Утепление","СУ Эдельвейс","эт2, эт3, эт4","эт2-50%, эт3-50%, эт4-50%","▌Фасады с лесов. Утепление","эт2, эт3, эт4"]
[74,"▌Фасады с лесов. Армировка","СУ Эдельвейс",null,null,"▌Фасады с лесов. Армировка","эт2, эт3, эт4"]
[149,"Мусоросборная камера"," ",null,null,"Мусоросборная камера","Черн. отд., ОВ ВК"]
["Секция 9"]
[66,"Стяжка квартир и МОП","Гарант Строй Сервис","эт4","эт4","Стяжка квартир и МОП"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)","эт1, эт2, эт3","эт1-90%, эт2-90%, эт3-0%","Вмазка коробок и квартирных щитов","эт1, эт2, эт3, эт4"]
[68,"Этажные щиты ЭО и СС в МОП","ГПК Инжпетрострой (электрика)","эт1, эт2, эт3","эт1-0%, эт2-0%, эт3-0%","Этажные щиты ЭО и СС в МОП","эт1, эт2, эт3, эт4"]
[69,"Клапаны ПД и ДУ","СК ИнжСтрой",null,null,"Клапаны ПД и ДУ","эт3"]
[71,"Двери технические и МОП","ТОУН СПб","подвал","подвал-0%","Двери технические и МОП","подвал"]
[72,"Монтаж коллекторов","СК ИнжСтрой","эт1, эт2","эт1-0%, эт2","Монтаж коллекторов","эт1, эт4"]
[73,"▌Фасады с лесов. Утепление","СУ Эдельвейс","эт2, эт3, эт4","эт2-0%, эт3-0%, эт4-0%","▌Фасады с лесов. Утепление","эт2, эт3, эт4"]
[74,"▌Фасады с лесов. Армировка","СУ Эдельвейс",null,null,"▌Фасады с лесов. Армировка","эт2, эт3, эт4"]
[149,"Мусоросборная камера"," ",null,null,"Мусоросборная камера","Черн. отд., ОВ ВК"]
["НС-3. Резиденции. Уч. 26 / 6-я оч. / Корпус 6.3"]
["Секция 1"]
[42,"▌Фасады на балконах. Окраска 1й слой","Арсенал Строй","эт1, эт2, эт3, эт4","эт1-0%, эт2-0%, эт3-0%, эт4-0%","▌Фасады на балконах. Окраска 1й слой","эт1, эт2, эт3, эт4"]
[53,"▲ Кровля. Окрытие парапета","МОСТ-СПБ",null,null,"▲ Кровля. Окрытие парапета","кровля"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)",null,null,"Вмазка коробок и квартирных щитов","эт3, эт4"]
[68,"Этажные щиты ЭО и СС в МОП","ГПК Инжпетрострой (электрика)","эт1, эт2","эт1-0%, эт2-0%","Этажные щиты ЭО и СС в МОП","эт1, эт2, эт3, эт4"]
[71,"Двери технические и МОП","ТОУН СПб","эт2","эт2-0%","Двери технические и МОП","эт2, эт3, эт4"]
[72,"Монтаж коллекторов","ГПК Инжпетрострой (сантехника)","эт4","эт4","Монтаж коллекторов"]
[74,"▌Фасады с лесов. Армировка","Арсенал Строй","эт2, эт3, эт4","эт2-90%, эт3-90%, эт4-90%","▌Фасады с лесов. Армировка","эт2, эт3, эт4"]
[75,"▌Фасады с лесов. Декор","Арсенал Строй","эт2, эт3, эт4","эт2-90%, эт3-90%, эт4-90%","▌Фасады с лесов. Декор","эт2, эт3, эт4, кровля"]
[82,"▦ Витражи каркасы","Энсейв Констракшн",null,null,"▦ Витражи каркасы","эт2"]
[96,"Лифты. Кронштейны и направляющие"," ",null,null,"Лифты. Кронштейны и направляющие","эт1, эт2, эт3, эт4"]
[149,"Мусоросборная камера"," ","Черн. отд., Чист. отд.","Черн. отд., Чист. отд.-0%","Мусоросборная камера","Чист. отд., ОВ ВК"]
["Секция 2"]
[42,"▌Фасады на балконах. Окраска 1й слой","Арсенал Строй",null,null,"▌Фасады на балконах. Окраска 1й слой","эт1, эт2, эт3, эт4"]
[66,"Стяжка квартир и МОП","ЭлитМастерПроект","эт3, эт4","эт3, эт4-50%","Стяжка квартир и МОП","эт4"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)",null,null,"Вмазка коробок и квартирных щитов","эт1, эт2, эт3"]
[68,"Этажные щиты ЭО и СС в МОП","ГПК Инжпетрострой (электрика)",null,null,"Этажные щиты ЭО и СС в МОП","эт1, эт2, эт3"]
[69,"Клапаны ПД и ДУ","ГПК Инжпетрострой (сантехника)","эт4","эт4","Клапаны ПД и ДУ"]
[71,"Двери технические и МОП","ТОУН СПб",null,null,"Двери технические и МОП","эт2, эт3, эт4"]
[72,"Монтаж коллекторов","ГПК Инжпетрострой (сантехника)","эт2, эт3, эт4","эт2, эт3, эт4","Монтаж коллекторов"]
[75,"▌Фасады с лесов. Декор","Арсенал Строй",null,null,"▌Фасады с лесов. Декор","эт2, эт3, эт4"]
[96,"Лифты. Кронштейны и направляющие"," ",null,null,"Лифты. Кронштейны и направляющие","эт1, эт2, эт3, эт4"]
[149,"Мусоросборная камера"," ","Черн. отд.","Черн. отд.-0%","Мусоросборная камера","Черн. отд., Чист. отд., ОВ ВК"]
["Секция 3"]
[42,"▌Фасады на балконах. Окраска 1й слой","Арсенал Строй",null,null,"▌Фасады на балконах. Окраска 1й слой","эт1, эт2, эт3, эт4"]
[61,"✱ Штукатурка стен вкруг и потолков","ЭлитМастерПроект","эт4","эт4-50%","✱ Штукатурка стен вкруг и потолков","эт4"]
[62,"Монтаж подложки под PEX","ЭлитМастерПроект","эт2, эт3, эт4","эт2, эт3-0%, эт4-0%","Монтаж подложки под PEX","эт3, эт4"]
[63,"Монтаж радиаторов","ГПК Инжпетрострой (сантехника)","эт1, эт2","эт1, эт2","Монтаж радиаторов","эт3, эт4"]
[64,"Монтаж PEX","ГПК Инжпетрострой (сантехника)","эт1, эт2","эт1, эт2","Монтаж PEX","эт3, эт4"]
[65,"Пневмоиспытания труб отопления","ГПК Инжпетрострой (сантехника)","эт1","эт1","Пневмоиспытания труб отопления","эт3, эт4"]
[66,"Стяжка квартир и МОП","ЭлитМастерПроект","эт1","эт1-0%","Стяжка квартир и МОП","эт1, эт2, эт3"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)",null,null,"Вмазка коробок и квартирных щитов","эт1, эт2"]
[68,"Этажные щиты ЭО и СС в МОП","ГПК Инжпетрострой (электрика)",null,null,"Этажные щиты ЭО и СС в МОП","эт1, эт2"]
[69,"Клапаны ПД и ДУ","ГПК Инжпетрострой (сантехника)","эт1, эт2","эт1, эт2","Клапаны ПД и ДУ","эт4"]
[70,"Штукатурка лестниц","ЭлитМастерПроект","эт4","эт4-0%","Штукатурка лестниц","эт4"]
[71,"Двери технические и МОП","ТОУН СПб",null,null,"Двери технические и МОП","эт2, эт3"]
[72,"Монтаж коллекторов","ГПК Инжпетрострой (сантехника)",null,null,"Монтаж коллекторов","эт3, эт4"]
[73,"▌Фасады с лесов. Утепление","Арсенал Строй",null,null,"▌Фасады с лесов. Утепление","эт2, эт3, эт4"]
[96,"Лифты. Кронштейны и направляющие"," ",null,null,"Лифты. Кронштейны и направляющие","эт1, эт2, эт3, эт4"]
[144,"ИТП жилых помещений"," ",null,null,"ИТП жилых помещений","Постав. обор."]
[146,"Водомерный узел"," ","Монт. обор.","Монт. обор.","Водомерный узел"]
[149,"Мусоросборная камера"," ",null,null,"Мусоросборная камера","Черн. отд., Чист. отд."]
["Секция 4"]
[19,"● Подвал. Трубопровод системы отопления","ГПК Инжпетрострой (сантехника)","подвал","подвал","● Подвал. Трубопровод системы отопления"]
[36,"Линейный монтаж АППЗ квартир и МОП"," ","эт1, эт2, эт3, эт4","эт1-0%, эт2-0%, эт3-0%, эт4-0%","Линейный монтаж АППЗ квартир и МОП","эт1, эт2, эт3, эт4"]
[40,"▌Фасады на балконах. Армировка","Арсенал Строй","эт2, эт3, эт4","эт2, эт3, эт4","▌Фасады на балконах. Армировка"]
[41,"▌Фасады на балконах. Декор","Арсенал Строй","эт1, эт2, эт3, эт4","эт1-0%, эт2-0%, эт3-0%, эт4-0%","▌Фасады на балконах. Декор","эт1, эт2, эт3, эт4"]
[61,"✱ Штукатурка стен вкруг и потолков","ЭлитМастерПроект","эт1","эт1-75%","✱ Штукатурка стен вкруг и потолков","эт1, эт2"]
[62,"Монтаж подложки под PEX","ЭлитМастерПроект",null,null,"Монтаж подложки под PEX","эт2"]
[63,"Монтаж радиаторов","ГПК Инжпетрострой (сантехника)",null,null,"Монтаж радиаторов","эт1, эт2"]
[64,"Монтаж PEX","ГПК Инжпетрострой (сантехника)",null,null,"Монтаж PEX","эт1, эт2"]
[65,"Пневмоиспытания труб отопления","ГПК Инжпетрострой (сантехника)",null,null,"Пневмоиспытания труб отопления","эт1, эт2"]
[79,"▌Фасады НВФ. Направляющие","Арсенал Строй","эт2, эт3, эт4","эт2, эт3, эт4","▌Фасады НВФ. Направляющие"]
[149,"Мусоросборная камера"," ",null,null,"Мусоросборная камера","Черн. отд."]
[151,"ГРЩ"," ","Черн. отд., Вх. дверь, Чист. отд.","Черн. отд., Вх. дверь-0%, Чист. отд.-0%","ГРЩ","Вх. дверь, Чист. отд., Постав. обор."]
["Секция 5"]
[41,"▌Фасады на балконах. Декор","Арсенал Строй","эт1, эт2, эт3, эт4","эт1-0%, эт2-0%, эт3-0%, эт4-0%","▌Фасады на балконах. Декор","эт1, эт2, эт3, эт4"]
[61,"✱ Штукатурка стен вкруг и потолков","ЭлитМастерПроект",null,null,"✱ Штукатурка стен вкруг и потолков","эт1, эт2"]
[62,"Монтаж подложки под PEX","ЭлитМастерПроект",null,null,"Монтаж подложки под PEX","эт2"]
[63,"Монтаж радиаторов","ГПК Инжпетрострой (сантехника)",null,null,"Монтаж радиаторов","эт1"]
[78,"▌Фасады НВФ. Утепление","Арсенал Строй","эт4","эт4","▌Фасады НВФ. Утепление"]
[79,"▌Фасады НВФ. Направляющие","Арсенал Строй","эт2, эт3, эт4","эт2-0%, эт3-0%, эт4-0%","▌Фасады НВФ. Направляющие","эт2, эт3, эт4"]
["Секция 6"]
[61,"✱ Штукатурка стен вкруг и потолков","ЭлитМастерПроект",null,null,"✱ Штукатурка стен вкруг и потолков","эт1"]
[63,"Монтаж радиаторов","ГПК Инжпетрострой (сантехника)",null,null,"Монтаж радиаторов","эт1"]
[64,"Монтаж PEX","ГПК Инжпетрострой (сантехника)",null,null,"Монтаж PEX","эт1"]
[65,"Пневмоиспытания труб отопления","ГПК Инжпетрострой (сантехника)",null,null,"Пневмоиспытания труб отопления","эт1"]
[72,"Монтаж коллекторов","ГПК Инжпетрострой (сантехника)",null,null,"Монтаж коллекторов","эт1"]
[74,"▌Фасады с лесов. Армировка","Арсенал Строй",null,null,"▌Фасады с лесов. Армировка","кровля"]
[78,"▌Фасады НВФ. Утепление","Арсенал Строй","эт2, эт3, эт4","эт2, эт3, эт4","▌Фасады НВФ. Утепление"]
[79,"▌Фасады НВФ. Направляющие","Арсенал Строй","эт2, эт3, эт4","эт2-0%, эт3-0%, эт4-0%","▌Фасады НВФ. Направляющие","эт2, эт3, эт4"]
["Секция 7"]
[42,"▌Фасады на балконах. Окраска 1й слой","Арсенал Строй",null,null,"▌Фасады на балконах. Окраска 1й слой","эт1, эт2, эт3, эт4"]
[61,"✱ Штукатурка стен вкруг и потолков","ЭлитМастерПроект","эт2, эт3, эт4","эт2-90%, эт3-0%, эт4-0%","✱ Штукатурка стен вкруг и потолков","эт2, эт3, эт4"]
[62,"Монтаж подложки под PEX","ЭлитМастерПроект","эт2","эт2-0%","Монтаж подложки под PEX","эт2, эт3, эт4"]
[63,"Монтаж радиаторов","ГПК Инжпетрострой (сантехника)","эт1","эт1","Монтаж радиаторов","эт2, эт3, эт4"]
[64,"Монтаж PEX","ГПК Инжпетрострой (сантехника)","эт1","эт1","Монтаж PEX","эт2, эт3"]
[65,"Пневмоиспытания труб отопления","ГПК Инжпетрострой (сантехника)","эт1","эт1","Пневмоиспытания труб отопления","эт2, эт3"]
[66,"Стяжка квартир и МОП","ЭлитМастерПроект",null,null,"Стяжка квартир и МОП","эт1, эт2"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)",null,null,"Вмазка коробок и квартирных щитов","эт1"]
[68,"Этажные щиты ЭО и СС в МОП","ГПК Инжпетрострой (электрика)",null,null,"Этажные щиты ЭО и СС в МОП","эт1"]
[69,"Клапаны ПД и ДУ","ГПК Инжпетрострой (сантехника)",null,null,"Клапаны ПД и ДУ","эт1, эт2"]
[70,"Штукатурка лестниц","ЭлитМастерПроект",null,null,"Штукатурка лестниц","эт2, эт3, эт4"]
[74,"▌Фасады с лесов. Армировка","Арсенал Строй","эт2, эт3, эт4","эт2, эт3, эт4","▌Фасады с лесов. Армировка","кровля"]
[75,"▌Фасады с лесов. Декор","Арсенал Строй",null,null,"▌Фасады с лесов. Декор","эт2, эт3, эт4, кровля"]
[78,"▌Фасады НВФ. Утепление","Арсенал Строй","эт2, эт4","эт2, эт4","▌Фасады НВФ. Утепление"]
[79,"▌Фасады НВФ. Направляющие","Арсенал Строй","эт2, эт3, эт4","эт2-0%, эт3-0%, эт4-0%","▌Фасады НВФ. Направляющие","эт2, эт3, эт4"]
[149,"Мусоросборная камера"," ","Вх. дверь","Вх. дверь","Мусоросборная камера","Черн. отд., Чист. отд."]
[151,"ГРЩ"," ","Черн. отд., Вх. дверь, Чист. отд.","Черн. отд., Вх. дверь-0%, Чист. отд.-0%","ГРЩ","Вх. дверь, Чист. отд., Постав. обор."]
["Секция 8"]
[42,"▌Фасады на балконах. Окраска 1й слой","Арсенал Строй",null,null,"▌Фасады на балконах. Окраска 1й слой","эт1, эт2, эт3, эт4"]
[61,"✱ Штукатурка стен вкруг и потолков","ЭлитМастерПроект","эт2, эт3, эт4","эт2, эт3-50%, эт4-0%","✱ Штукатурка стен вкруг и потолков","эт3, эт4"]
[62,"Монтаж подложки под PEX","ЭлитМастерПроект","эт2, эт3","эт2-0%, эт3-0%","Монтаж подложки под PEX","эт2, эт3, эт4"]
[63,"Монтаж радиаторов","ГПК Инжпетрострой (сантехника)","эт1","эт1","Монтаж радиаторов","эт2, эт3, эт4"]
[64,"Монтаж PEX","ГПК Инжпетрострой (сантехника)","эт1","эт1","Монтаж PEX","эт2, эт3"]
[65,"Пневмоиспытания труб отопления","ГПК Инжпетрострой (сантехника)","эт1","эт1","Пневмоиспытания труб отопления","эт2, эт3"]
[66,"Стяжка квартир и МОП","ЭлитМастерПроект","эт1","эт1-0%","Стяжка квартир и МОП","эт1, эт2"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)",null,null,"Вмазка коробок и квартирных щитов","эт1"]
[68,"Этажные щиты ЭО и СС в МОП","ГПК Инжпетрострой (электрика)",null,null,"Этажные щиты ЭО и СС в МОП","эт1"]
[69,"Клапаны ПД и ДУ","ГПК Инжпетрострой (сантехника)","эт1, эт2","эт1, эт2","Клапаны ПД и ДУ","эт3"]
[70,"Штукатурка лестниц","ЭлитМастерПроект","эт2","эт2","Штукатурка лестниц","эт3, эт4"]
[72,"Монтаж коллекторов","ГПК Инжпетрострой (сантехника)",null,null,"Монтаж коллекторов","эт1, эт2, эт3, эт4"]
[75,"▌Фасады с лесов. Декор","Арсенал Строй","эт2, эт3, эт4","эт2, эт3, эт4","▌Фасады с лесов. Декор"]
[79,"▌Фасады НВФ. Направляющие","Арсенал Строй","эт2, эт3, эт4","эт2-0%, эт3-0%, эт4-0%","▌Фасады НВФ. Направляющие","эт2, эт3, эт4"]
[149,"Мусоросборная камера"," ","Вх. дверь","Вх. дверь","Мусоросборная камера","Черн. отд., Чист. отд."]
["НС-3. Резиденции. Уч. 26 / 6-я оч. / Корпус 6.4"]
["Секция 1"]
[30,"Монтаж окон","СК Козерог",null,null,"Монтаж окон","подвал"]
[41,"▌Фасады на балконах. Декор","СУ Эдельвейс","эт2","эт2","▌Фасады на балконах. Декор"]
[62,"Монтаж подложки под PEX"," ","эт4","эт4","Монтаж подложки под PEX"]
[65,"Пневмоиспытания труб отопления","ГПК Инжпетрострой (сантехника)","эт4","эт4","Пневмоиспытания труб отопления"]
[66,"Стяжка квартир и МОП"," ","эт3, эт4","эт3, эт4","Стяжка квартир и МОП"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)",null,null,"Вмазка коробок и квартирных щитов","эт1"]
[68,"Этажные щиты ЭО и СС в МОП","ГПК Инжпетрострой (электрика)",null,null,"Этажные щиты ЭО и СС в МОП","эт1"]
[69,"Клапаны ПД и ДУ","ГПК Инжпетрострой (сантехника)","эт1, эт2, эт3, эт4","эт1, эт2, эт3, эт4","Клапаны ПД и ДУ"]
[73,"▌Фасады с лесов. Утепление","СУ Эдельвейс","эт2, эт3, эт4","эт2-50%, эт3-50%, эт4-50%","▌Фасады с лесов. Утепление","эт2, эт3, эт4"]
[74,"▌Фасады с лесов. Армировка","СУ Эдельвейс",null,null,"▌Фасады с лесов. Армировка","эт2, эт3, эт4"]
[77,"▌Фасады НВФ. Кронштейны","СУ Эдельвейс","эт1, эт2, эт3, эт4","эт1-0%, эт2-0%, эт3-0%, эт4-0%","▌Фасады НВФ. Кронштейны","эт1, эт2, эт3, эт4"]
[78,"▌Фасады НВФ. Утепление","СУ Эдельвейс",null,null,"▌Фасады НВФ. Утепление","эт1, эт2, эт3, эт4"]
[149,"Мусоросборная камера"," ","Чист. отд.","Чист. отд.-0%","Мусоросборная камера","Чист. отд., ОВ ВК"]
[151,"ГРЩ"," ","Черн. отд., Вх. дверь, Чист. отд.","Черн. отд.-0%, Вх. дверь-0%, Чист. отд.-0%","ГРЩ","Черн. отд., Вх. дверь, Чист. отд., Постав. обор."]
["Секция 2"]
[61,"✱ Штукатурка стен вкруг и потолков"," ","эт4","эт4","✱ Штукатурка стен вкруг и потолков"]
[62,"Монтаж подложки под PEX"," ","эт3, эт4","эт3, эт4","Монтаж подложки под PEX"]
[63,"Монтаж радиаторов","ГПК Инжпетрострой (сантехника)","эт3, эт4","эт3, эт4","Монтаж радиаторов"]
[64,"Монтаж PEX","ГПК Инжпетрострой (сантехника)","эт3","эт3","Монтаж PEX"]
[65,"Пневмоиспытания труб отопления","ГПК Инжпетрострой (сантехника)","эт3","эт3","Пневмоиспытания труб отопления"]
[66,"Стяжка квартир и МОП"," ","эт1, эт2","эт1, эт2","Стяжка квартир и МОП","эт3, эт4"]
[69,"Клапаны ПД и ДУ","ГПК Инжпетрострой (сантехника)","эт2","эт2","Клапаны ПД и ДУ"]
[70,"Штукатурка лестниц"," ","эт1, эт2, эт3, эт4","эт1, эт2, эт3, эт4","Штукатурка лестниц"]
[73,"▌Фасады с лесов. Утепление","СУ Эдельвейс","эт2, эт3, эт4","эт2-10%, эт3-10%, эт4-10%","▌Фасады с лесов. Утепление","эт2, эт3, эт4"]
[74,"▌Фасады с лесов. Армировка","СУ Эдельвейс",null,null,"▌Фасады с лесов. Армировка","эт2, эт3, эт4"]
[77,"▌Фасады НВФ. Кронштейны","СУ Эдельвейс","эт1, эт2, эт3, эт4","эт1-0%, эт2-0%, эт3-0%, эт4-0%","▌Фасады НВФ. Кронштейны","эт1, эт2, эт3, эт4"]
[78,"▌Фасады НВФ. Утепление","СУ Эдельвейс",null,null,"▌Фасады НВФ. Утепление","эт1, эт2, эт3, эт4"]
["Секция 3"]
[12,"Монолитные приямки","ГПК Инжпетрострой (монолит)",null,null,"Монолитные приямки","подвал"]
[30,"Монтаж окон","СК Козерог",null,null,"Монтаж окон","подвал"]
[63,"Монтаж радиаторов","ГПК Инжпетрострой (сантехника)","эт4","эт4","Монтаж радиаторов"]
[64,"Монтаж PEX","ГПК Инжпетрострой (сантехника)","эт4","эт4","Монтаж PEX"]
[65,"Пневмоиспытания труб отопления","ГПК Инжпетрострой (сантехника)","эт4","эт4","Пневмоиспытания труб отопления"]
[66,"Стяжка квартир и МОП"," ","эт2","эт2","Стяжка квартир и МОП","эт3, эт4"]
[71,"Двери технические и МОП","ССП Групп",null,null,"Двери технические и МОП","подвал"]
[73,"▌Фасады с лесов. Утепление","СУ Эдельвейс",null,null,"▌Фасады с лесов. Утепление","эт2, эт3, эт4"]
[77,"▌Фасады НВФ. Кронштейны","СУ Эдельвейс",null,null,"▌Фасады НВФ. Кронштейны","эт1, эт2, эт3, эт4"]
[144,"ИТП жилых помещений"," ",null,null,"ИТП жилых помещений","Постав. обор."]
[149,"Мусоросборная камера"," ",null,null,"Мусоросборная камера","ОВ ВК"]
["Секция 4"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)","эт1","эт1-0%","Вмазка коробок и квартирных щитов","эт1, эт2, эт3, эт4"]
[68,"Этажные щиты ЭО и СС в МОП","ГПК Инжпетрострой (электрика)","эт1","эт1-0%","Этажные щиты ЭО и СС в МОП","эт1, эт2, эт3, эт4"]
[73,"▌Фасады с лесов. Утепление","СУ Эдельвейс",null,null,"▌Фасады с лесов. Утепление","эт2, эт3, эт4"]
[78,"▌Фасады НВФ. Утепление","СУ Эдельвейс",null,null,"▌Фасады НВФ. Утепление","эт1"]
[79,"▌Фасады НВФ. Направляющие","СУ Эдельвейс",null,null,"▌Фасады НВФ. Направляющие","эт1"]
[149,"Мусоросборная камера"," ",null,null,"Мусоросборная камера","ОВ ВК"]
["Секция 5"]
[12,"Монолитные приямки","ГПК Инжпетрострой (монолит)",null,null,"Монолитные приямки","подвал"]
[66,"Стяжка квартир и МОП"," ","эт4","эт4","Стяжка квартир и МОП"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)","эт1, эт2, эт3","эт1, эт2, эт3-0%","Вмазка коробок и квартирных щитов","эт3, эт4"]
[68,"Этажные щиты ЭО и СС в МОП","ГПК Инжпетрострой (электрика)","эт1, эт2, эт3","эт1-0%, эт2-0%, эт3-0%","Этажные щиты ЭО и СС в МОП","эт1, эт2, эт3, эт4"]
[71,"Двери технические и МОП","ССП Групп",null,null,"Двери технические и МОП","подвал"]
[78,"▌Фасады НВФ. Утепление","СУ Эдельвейс",null,null,"▌Фасады НВФ. Утепление","эт1"]
[79,"▌Фасады НВФ. Направляющие","СУ Эдельвейс",null,null,"▌Фасады НВФ. Направляющие","эт1"]
[80,"▌Фасады НВФ. Монтаж керамогранита","СУ Эдельвейс","эт2, эт3, эт4","эт2, эт3, эт4","▌Фасады НВФ. Монтаж керамогранита"]
[82,"▦ Витражи каркасы","Энсейв Констракшн",null,null,"▦ Витражи каркасы","эт2"]
["Секция 6"]
[18,"● Подвал. Трубопровод системы водоснабжения","ГПК Инжпетрострой (сантехника)","подвал","подвал","● Подвал. Трубопровод системы водоснабжения"]
[66,"Стяжка квартир и МОП"," ","эт4","эт4","Стяжка квартир и МОП"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)",null,null,"Вмазка коробок и квартирных щитов","эт1"]
[68,"Этажные щиты ЭО и СС в МОП","ГПК Инжпетрострой (электрика)",null,null,"Этажные щиты ЭО и СС в МОП","эт1"]
[69,"Клапаны ПД и ДУ","ГПК Инжпетрострой (сантехника)","эт1, эт2, эт3, эт4","эт1, эт2, эт3, эт4","Клапаны ПД и ДУ"]
[78,"▌Фасады НВФ. Утепление","СУ Эдельвейс","эт1","эт1","▌Фасады НВФ. Утепление"]
[79,"▌Фасады НВФ. Направляющие","СУ Эдельвейс","эт1","эт1","▌Фасады НВФ. Направляющие"]
[80,"▌Фасады НВФ. Монтаж керамогранита","СУ Эдельвейс","эт1, эт2, эт3, эт4","эт1, эт2, эт3, эт4","▌Фасады НВФ. Монтаж керамогранита"]
[151,"ГРЩ"," ","Черн. отд.","Черн. отд.","ГРЩ","Постав. обор."]
["Секция 7"]
[68,"Этажные щиты ЭО и СС в МОП","ГПК Инжпетрострой (электрика)","эт1, эт2, эт3","эт1-0%, эт2-0%, эт3-0%","Этажные щиты ЭО и СС в МОП","эт1, эт2, эт3, эт4"]
[71,"Двери технические и МОП","ССП Групп",null,null,"Двери технические и МОП","подвал"]
[73,"▌Фасады с лесов. Утепление","СУ Эдельвейс","эт2, эт3, эт4","эт2-50%, эт3-50%, эт4-50%","▌Фасады с лесов. Утепление","эт2, эт3, эт4"]
[74,"▌Фасады с лесов. Армировка","СУ Эдельвейс","эт2, эт3, эт4","эт2-0%, эт3-0%, эт4-0%","▌Фасады с лесов. Армировка","эт2, эт3, эт4"]
[75,"▌Фасады с лесов. Декор","СУ Эдельвейс",null,null,"▌Фасады с лесов. Декор","эт2, эт3, эт4"]
[78,"▌Фасады НВФ. Утепление","СУ Эдельвейс","эт1","эт1","▌Фасады НВФ. Утепление"]
[79,"▌Фасады НВФ. Направляющие","СУ Эдельвейс","эт1","эт1","▌Фасады НВФ. Направляющие"]
[80,"▌Фасады НВФ. Монтаж керамогранита","СУ Эдельвейс","эт1, эт2, эт3, эт4","эт1, эт2, эт3, эт4","▌Фасады НВФ. Монтаж керамогранита"]
[146,"Водомерный узел"," ","Черн. отд., Чист. отд.","Черн. отд.-0%, Чист. отд.-0%","Водомерный узел","Черн. отд., Чист. отд., Постав. обор."]
[149,"Мусоросборная камера"," ",null,null,"Мусоросборная камера","Чист. отд."]
["Секция 8"]
[33,"Монтаж вентиляционных отводов с/у","ГПК Инжпетрострой (сантехника)","эт3, эт4","эт3, эт4","Монтаж вентиляционных отводов с/у"]
[41,"▌Фасады на балконах. Декор","СУ Эдельвейс","эт1, эт2, эт3, эт4","эт1, эт2, эт3, эт4","▌Фасады на балконах. Декор"]
[67,"Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)","эт4","эт4","Вмазка коробок и квартирных щитов"]
[68,"Этажные щиты ЭО и СС в МОП","ГПК Инжпетрострой (электрика)","эт1, эт2","эт1-0%, эт2-0%","Этажные щиты ЭО и СС в МОП","эт1, эт2, эт3, эт4"]
[71,"Двери технические и МОП","ССП Групп",null,null,"Двери технические и МОП","подвал"]
[72,"Монтаж коллекторов","ГПК Инжпетрострой (сантехника)",null,null,"Монтаж коллекторов","эт1, эт2"]
[73,"▌Фасады с лесов. Утепление","СУ Эдельвейс","эт2, эт3, эт4","эт2-50%, эт3-50%, эт4-50%","▌Фасады с лесов. Утепление","эт2, эт3, эт4"]
[74,"▌Фасады с лесов. Армировка","СУ Эдельвейс","эт2, эт3, эт4","эт2-50%, эт3-50%, эт4-50%","▌Фасады с лесов. Армировка","эт2, эт3, эт4"]
[75,"▌Фасады с лесов. Декор","СУ Эдельвейс",null,null,"▌Фасады с лесов. Декор","эт2, эт3, эт4"]
[78,"▌Фасады НВФ. Утепление","СУ Эдельвейс","эт1","эт1","▌Фасады НВФ. Утепление"]
[79,"▌Фасады НВФ. Направляющие","СУ Эдельвейс","эт1, эт2, эт3, эт4","эт1-0%, эт2-0%, эт3-0%, эт4-0%","▌Фасады НВФ. Направляющие","эт1, эт2, эт3, эт4"]
[80,"▌Фасады НВФ. Монтаж керамогранита","СУ Эдельвейс",null,null,"▌Фасады НВФ. Монтаж керамогранита","эт1, эт2, эт3, эт4"]
[149,"Мусоросборная камера"," ",null,null,"Мусоросборная камера","Чист. отд."]

{"sheet":"Эф. по корпусам","index":3,"n_rows":38,"n_cols":4,"rows_kept":38,"cut":false,"hidden":false,"merged":[]}
[{"$f":"Объект","v":"НС-3. Резиденции. Уч. 26 / 6-я оч."},null,null,{"$f":"TEXT(дата_совещания[]-8,\"ДД.ММ.ГГГГ\")&\" - \"&TEXT(дата_совещания[]-1,\"ДД.ММ.ГГГГ\")","v":"12.09.2022 - 19.09.2022"}]
[{"$f":"\"Эффективность выполнения задач за неделю = \"&TEXT(GETPIVOTDATA(\"[Measures].[Эффективность]\",$A$3),\"00%\")","v":"Эффективность выполнения задач за неделю = 37%"}]
["Корпус, подрядчик","Всего задач","Выполнено","Эффективность"]
["НС-3. Резиденции. Уч. 26 / 6-я оч. / Корпус 6.1",363,107,0.29476584022038566]
["(пусто)",46,12,0.2608695652173913]
["Арсенал Строй",121,16,0.13223140495867769]
["ГПК Инжпетрострой (металл)",20,14,0.7]
["ГПК Инжпетрострой (электрика)",20,7,0.35]
["Ленстройгрупп",2,1,0.5]
["СК Интеп",12,0,0]
["ССП Групп",42,19,0.45238095238095238]
["СТР",21,0,0]
["ТРАСТ",53,38,0.71698113207547165]
["ЭнергоПроектСтрой",10,0,0]
["Энсейв Констракшн",16,0,0]
["НС-3. Резиденции. Уч. 26 / 6-я оч. / Корпус 6.2",196,72,0.36734693877551022]
["(пусто)",48,8,0.16666666666666666]
["Гарант Строй Сервис",12,8,0.66666666666666663]
["ГПК Инжпетрострой (электрика)",16,11,0.6875]
["СК ИнжСтрой",40,20,0.5]
["СУ Эдельвейс",54,6,0.1111111111111111]
["ТОУН СПб",8,5,0.625]
["Фаст Компани",18,14,0.77777777777777779]
["НС-3. Резиденции. Уч. 26 / 6-я оч. / Корпус 6.3",122,61,0.5]
["(пусто)",21,10,0.47619047619047616]
["Арсенал Строй",50,26,0.52]
["ГПК Инжпетрострой (сантехника)",21,21,1]
["ГПК Инжпетрострой (электрика)",3,0,0]
["ТОУН СПб",1,0,0]
["ЭлитМастерПроект",26,4,0.15384615384615385]
["НС-3. Резиденции. Уч. 26 / 6-я оч. / Корпус 6.4",136,64,0.47058823529411764]
["(пусто)",30,16,0.53333333333333333]
["ГПК Инжпетрострой (монолит)",2,0,0]
["ГПК Инжпетрострой (сантехника)",22,21,0.95454545454545459]
["ГПК Инжпетрострой (электрика)",14,3,0.21428571428571427]
["СК Козерог",2,0,0]
["СУ Эдельвейс",66,24,0.36363636363636365]
["Общий итог",817,304,0.37209302325581395]

{"sheet":"Эф. по подр.","index":4,"n_rows":24,"n_cols":4,"rows_kept":24,"cut":false,"hidden":false,"merged":[]}
[{"$f":"Объект","v":"НС-3. Резиденции. Уч. 26 / 6-я оч."},null,null,{"$f":"TEXT(дата_совещания[]-8,\"ДД.ММ.ГГГГ\")&\" - \"&TEXT(дата_совещания[]-1,\"ДД.ММ.ГГГГ\")","v":"12.09.2022 - 19.09.2022"}]
[{"$f":"\"Эффективность выполнения задач за неделю = \"&TEXT(GETPIVOTDATA(\"[Measures].[Эффективность]\",$A$3),\"00%\")","v":"Эффективность выполнения задач за неделю = 37%"}]
["Корпус, подрядчик","Всего задач","Выполнено","Эффективность"]
["ГПК Инжпетрострой (сантехника)",43,42,0.97674418604651159]
["Фаст Компани",18,14,0.77777777777777779]
["ТРАСТ",53,38,0.71698113207547165]
["ГПК Инжпетрострой (металл)",20,14,0.7]
["Гарант Строй Сервис",12,8,0.66666666666666663]
["ТОУН СПб",9,5,0.55555555555555558]
["СК ИнжСтрой",40,20,0.5]
["Ленстройгрупп",2,1,0.5]
["ССП Групп",42,19,0.45238095238095238]
["ГПК Инжпетрострой (электрика)",53,21,0.39622641509433965]
["(пусто)",145,46,0.31724137931034485]
["СУ Эдельвейс",120,30,0.25]
["Арсенал Строй",171,42,0.24561403508771928]
["ЭлитМастерПроект",26,4,0.15384615384615385]
["СТР",21,0,0]
["СК Козерог",2,0,0]
["ЭнергоПроектСтрой",10,0,0]
["Энсейв Констракшн",16,0,0]
["ГПК Инжпетрострой (монолит)",2,0,0]
["СК Интеп",12,0,0]
["Общий итог",817,304,0.37209302325581395]

{"sheet":"График план-факт","index":5,"n_rows":2869,"n_cols":41,"rows_kept":2869,"cut":false,"hidden":false,"merged":[]}
[{"$f":"Объект","v":"НС-3. Резиденции. Уч. 26 / 6-я оч."},null,null,null,null,"— текущая дата"]
["График производства работ",null,null,null,null,"— + и - неделя"]
[]
[null,null,null,null,null,null,"Даты_графика"]
["Корпус","Работа","Подрядчик","Секция","qFloors.name","Значения","2022-06-13","2022-06-14","2022-06-15","2022-06-16","2022-06-17","2022-06-18","2022-06-19","2022-06-20","2022-06-21","2022-06-22","2022-06-23","2022-06-24","2022-06-25","2022-06-26","2022-06-27","2022-06-28","2022-06-29","2022-06-30","2022-07-01","2022-07-02","2022-07-03","2022-07-04","2022-07-05","2022-07-06","2022-07-07","2022-07-08","2022-07-09","2022-07-10","2022-07-11","2022-07-12","2022-07-13","2022-07-14","2022-07-15","2022-07-16","2022-07-17"]
["Корпус 6.1","013. Монолитные крыльца","ЭнергоПроектСтрой","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 5","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 6","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 9","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 10","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"015. ● Подвал. Лотки ЭО","ИНКОМ СПБ","Секция 1","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,"Секция 2","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,"Секция 3","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,"Секция 4","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,"Секция 5","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,"Секция 10","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,"020. Металлические решётки приямков в подвале","(пусто)","Секция 1","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0]
[null,null,null,"Секция 2","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,"Секция 3","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 4","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 5","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 6","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,"021. Металлические лестницы и ограждения в подвале","(пусто)","Секция 1","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0]
[null,null,null,"Секция 2","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,"Секция 3","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 4","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 5","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 6","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,"023. Подготовка монолита (шлифовка стен)","ЭнергоПроектСтрой","Секция 1","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 3","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 4","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 5","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 7","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 8","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 9","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 10","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"030. Монтаж окон","Окна Форте","Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"033. Монтаж вентиляционных отводов с/у","ТРАСТ","Секция 3","3","План",3,3]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,null,"4","План",4,4]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,"Секция 4","1","План",1,1,1]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,null,"2","План",2,2,2]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,null,"3","План",null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,100,100,100,100,100,100,100]
[null,null,null,"Секция 5","1","План",null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"035. Линейный монтаж проводов ЭО квартир","ИНКОМ СПБ","Секция 1","3","План",null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 2","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 3","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 4","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 5","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 6","1","План",null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 7","3","План",null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,"Секция 8","3","План",null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 9","1","План",null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 10","1","План",1]
[null,null,null,null,null,"Факт",100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,"036. Линейный монтаж АППЗ квартир и МОП","(пусто)","Секция 1","1","План",1,1,1,1]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,100,100,100,100]
[null,null,null,null,"3","План",null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,100,100,100,100]
[null,null,null,"Секция 2","2","План",null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 4","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 5","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 6","1","План",null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 7","1","План",1]
[null,null,null,null,null,"Факт",100]
[null,null,null,null,"2","План",2,2,2,2]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,"Секция 9","2","План",null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 10","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,"039. ▌Фасады на балконах. Утепление","Арсенал Строй","Секция 1","3","План",3,3]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,null,"4","План",4,4]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,"Секция 2","4","План",4,4]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,"Секция 3","1","План",1,1]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,null,"3","План",3,3]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,null,"4","План",4,4]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,"Секция 4","1","План",1,1]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,null,"3","План",3,3]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,null,"4","План",4,4]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,"Секция 5","4","План",4,4,4]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,"Секция 6","3","План",null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 7","4","План",4,4]
[null,null,null,null,null,"Факт",100,100]
[null,"040. ▌Фасады на балконах. Армировка","Арсенал Строй","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","3","План",null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 4","1","План",null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,100,100,100,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 5","2","План",null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,100,100,100,100,100,100,100]
[null,null,null,null,"3","План",null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,100,100,100,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","3","План",null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 7","4","План",null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 9","2","План",null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,100,100,100,100,100,100,100]
[null,null,null,null,"3","План",null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,100,100,100,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,50,50,50,50,50,50,50]
[null,null,null,"Секция 10","4","План",null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,90,90,90,90,90,90,90]
[null,"041. ▌Фасады на балконах. Декор","Арсенал Строй","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","2","План",null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 4","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 5","1","План",null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","3","План",null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 7","4","План",null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 9","1","План",null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 10","3","План",null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"049. ▲ Кровля. Гидроизоляция нижний слой","СК Интеп","Секция 3","кр","План","кр","кр","кр"]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,"Секция 4","кр","План","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",100,100,100,100,100,100]
[null,null,null,"Секция 5","кр","План",null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,100,100,100,100,100,100,100]
[null,"050. ▲ Кровля. Гидроизоляция вентшахт","СК Интеп","Секция 1","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 3","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,"Секция 4","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 7","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 8","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 9","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 10","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"056. Кабельные линии ЭО фасадов","ИНКОМ СПБ","Секция 4","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 5","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"058. Монтаж МК балконов и лоджий","(пусто)","Секция 2","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 10","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"060. Штукатурка стен вкруг и потолков","Ленстройгрупп","Секция 1","1","План",1,1,1]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,null,"2","План",null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,100,100,100,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 3","1","План",null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 4","1","План",null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 10","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,"СТР","Секция 5","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 6","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 7","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 8","3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 9","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"061. Штукатурка лестниц","Ленстройгрупп","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,"СТР","Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"062. Монтаж радиаторов","ТРАСТ","Секция 1","1","План",null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 2","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 4","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 5","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 6","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 8","1","План",null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 9","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 10","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,"063. Монтаж коллекторов","ТРАСТ","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 4","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 5","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 10","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,"064. Монтаж подложки под PEX","Ленстройгрупп","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 2","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 4","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 10","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,"СТР","Секция 5","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 6","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 9","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,"065. Монтаж PEX","ТРАСТ","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 4","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 5","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 6","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,75,75,75]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 9","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 10","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,"066. Пневмоиспытания труб отопления","ТРАСТ","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,100,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 4","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 5","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 6","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 9","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 10","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,"067. Стяжка квартир и МОП","Ленстройгрупп","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 4","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 10","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,"СТР","Секция 5","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 6","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 9","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,"068. Технические двери","(пусто)","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0]
[null,null,null,null,"кр","План",null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п","п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"кр","План",null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п","п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"кр","План",null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п","п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,"Секция 4","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"кр","План",null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п","п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,"Секция 5","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"кр","План",null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п","п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"кр","План",null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п","п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"кр","План",null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п","п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0]
[null,null,null,null,"кр","План",null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п","п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,"Секция 9","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"кр","План",null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п","п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,"Секция 10","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"кр","План",null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,null,"п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п","п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,"070. ▌Фасады с лесов. Утепление","Арсенал Строй","Секция 1","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 3","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,75,75,75,75,75,75,75]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,75,75,75,75,75,75,75]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,75,75,75,75,75,75,75]
[null,null,null,"Секция 4","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 5","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,75,75,75,75,75,75,75]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,75,75,75,75,75,75,75]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,75,75,75,75,75,75,75]
[null,null,null,"Секция 7","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 8","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,75,75,75,75,75,75,75]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,75,75,75,75,75,75,75]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,75,75,75,75,75,75,75]
[null,null,null,"Секция 9","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 10","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,"071. ▌Фасады с лесов. Армировка","Арсенал Строй","Секция 1","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 4","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 5","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 6","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,75,75,75]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,75,75,75]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,75,75,75]
[null,null,null,"Секция 7","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 8","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,75,75,75]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,75,75,75]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,75,75,75]
[null,"072. ▌Фасады с лесов. Декор","Арсенал Строй","Секция 1","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 4","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 5","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 6","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,75,75,75]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,75,75,75]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,75,75,75]
[null,null,null,"Секция 7","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 8","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,75,75,75]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,75,75,75]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,75,75,75]
[null,"073. ▌Фасады НВФ. Кронштейны","(пусто)","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"086. Вмазка коробок и квартирных щитов","ИНКОМ СПБ","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,"Секция 2","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 4","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 5","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,"Секция 6","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,"Секция 9","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 10","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,"142. ИТП жилых помещений","(пусто)","Секция 1","Вх. дверь","План",null,null,null,null,null,null,null,null,null,null,"Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"ОВ ВК","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"ОВ ВК","ОВ ВК","ОВ ВК","ОВ ВК","ОВ ВК","ОВ ВК","ОВ ВК"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"СС","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"СС","СС","СС","СС","СС","СС","СС"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"ФР для отд.","План",null,null,"ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд."]
[null,null,null,null,null,"Факт",null,null,100,100,100,100,100,100,100]
[null,null,null,null,"Черн. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,"Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Чист. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"ЭО","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"ЭО","ЭО","ЭО","ЭО","ЭО","ЭО","ЭО"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"143. ИТП встройки","(пусто)","Секция 2","Вх. дверь","План",null,null,null,null,null,null,null,null,null,null,"Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"ОВ ВК","План",null,null,null,null,null,null,null,null,null,null,"ОВ ВК","ОВ ВК","ОВ ВК","ОВ ВК","ОВ ВК","ОВ ВК","ОВ ВК"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"СС","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"СС","СС","СС","СС","СС","СС","СС"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"ФР для отд.","План",null,null,null,null,null,null,null,null,null,"ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Черн. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Чист. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"ЭО","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"ЭО","ЭО","ЭО","ЭО","ЭО","ЭО","ЭО"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"144. Водомерный узел","(пусто)","Секция 3","Вх. дверь","План",null,null,null,null,null,null,null,null,null,null,"Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Монт. обор.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Монт. обор.","Монт. обор.","Монт. обор.","Монт. обор.","Монт. обор.","Монт. обор.","Монт. обор."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"ОВ ВК","План",null,null,null,null,null,null,null,null,null,null,"ОВ ВК","ОВ ВК","ОВ ВК","ОВ ВК","ОВ ВК","ОВ ВК","ОВ ВК"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"Постав. обор.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Постав. обор.","Постав. обор.","Постав. обор.","Постав. обор.","Постав. обор.","Постав. обор.","Постав. обор."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"СС","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"СС","СС","СС","СС","СС","СС","СС"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"ФР для отд.","План",null,null,null,null,null,null,null,null,null,"ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Черн. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Чист. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"ЭО","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"ЭО","ЭО","ЭО","ЭО","ЭО","ЭО","ЭО"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"145. Насосная","(пусто)","Секция 3","Вх. дверь","План",null,null,null,null,null,null,null,null,null,null,"Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Монт. обор.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Монт. обор.","Монт. обор.","Монт. обор.","Монт. обор.","Монт. обор.","Монт. обор."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0]
[null,null,null,null,"ОВ ВК","План",null,null,null,null,null,null,null,null,null,null,"ОВ ВК","ОВ ВК","ОВ ВК","ОВ ВК","ОВ ВК","ОВ ВК","ОВ ВК"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"Постав. обор.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Постав. обор.","Постав. обор.","Постав. обор.","Постав. обор.","Постав. обор.","Постав. обор.","Постав. обор."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"СС","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"СС","СС","СС","СС","СС","СС","СС"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"ФР для отд.","План",null,null,null,null,null,null,null,null,null,"ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Черн. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Чист. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"ЭО","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"ЭО","ЭО","ЭО","ЭО","ЭО","ЭО","ЭО"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"146. Кабельная","(пусто)","Секция 1","Вх. дверь","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Черн. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","Вх. дверь","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Черн. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"147. Мусоросборная камера","(пусто)","Секция 1","Вх. дверь","План",null,null,null,null,null,null,null,null,null,"Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"СС","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"СС","СС","СС","СС","СС","СС","СС"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Черн. отд.","План",null,null,null,null,null,null,null,null,null,null,null,"Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Чист. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,"Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"ЭО","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"ЭО","ЭО","ЭО","ЭО","ЭО","ЭО","ЭО"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","Вх. дверь","План",null,null,null,null,null,null,null,null,null,"Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"СС","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"СС","СС","СС","СС","СС","СС","СС"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Черн. отд.","План",null,null,null,null,null,null,null,null,null,null,null,"Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Чист. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"ЭО","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"ЭО","ЭО","ЭО","ЭО","ЭО","ЭО","ЭО"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 3","Вх. дверь","План",null,null,null,null,null,null,null,null,null,"Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"СС","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"СС","СС","СС","СС","СС","СС","СС"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Черн. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Чист. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"ЭО","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"ЭО","ЭО","ЭО","ЭО","ЭО","ЭО","ЭО"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 4","Вх. дверь","План",null,null,null,null,null,null,null,null,null,"Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"СС","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"СС","СС","СС","СС","СС","СС","СС"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Черн. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Чист. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"ЭО","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"ЭО","ЭО","ЭО","ЭО","ЭО","ЭО","ЭО"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 5","Вх. дверь","План",null,null,null,null,null,null,null,null,null,"Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"СС","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"СС","СС","СС","СС","СС","СС","СС"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Черн. отд.","План",null,null,null,null,null,null,null,null,null,null,null,"Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Чист. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,"Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"ЭО","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"ЭО","ЭО","ЭО","ЭО","ЭО","ЭО","ЭО"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","Вх. дверь","План",null,null,null,null,null,null,null,null,null,"Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"СС","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"СС","СС","СС","СС","СС","СС","СС"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Черн. отд.","План",null,null,null,null,null,null,null,null,null,null,null,"Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Чист. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"ЭО","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"ЭО","ЭО","ЭО","ЭО","ЭО","ЭО","ЭО"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 7","Вх. дверь","План",null,null,null,null,null,null,null,null,null,"Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"СС","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"СС","СС","СС","СС","СС","СС","СС"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Черн. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,"Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Чист. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 8","Вх. дверь","План",null,null,null,null,null,null,null,null,null,"Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"СС","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"СС","СС","СС","СС","СС","СС","СС"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Черн. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Чист. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"ЭО","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"ЭО","ЭО","ЭО","ЭО","ЭО","ЭО","ЭО"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 9","Вх. дверь","План",null,null,null,null,null,null,null,null,null,"Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"СС","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"СС","СС","СС","СС","СС"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,null,"Черн. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Чист. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"ЭО","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"ЭО","ЭО","ЭО","ЭО","ЭО","ЭО","ЭО"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 10","Вх. дверь","План",null,null,null,null,null,null,null,null,null,"Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"СС","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"СС","СС","СС","СС","СС"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,null,"Черн. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Чист. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд.","Чист. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"ЭО","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"ЭО","ЭО","ЭО","ЭО","ЭО","ЭО","ЭО"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"149. ГРЩ","(пусто)","Секция 1","Вх. дверь","План",null,null,null,null,null,null,null,null,null,null,"Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"СС","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"СС","СС","СС","СС","СС","СС","СС"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"ФР для отд.","План",null,null,"ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд."]
[null,null,null,null,null,"Факт",null,null,100,100,100,100,100,100,100]
[null,null,null,null,"Черн. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"ЭО","План",null,null,null,null,null,null,null,null,null,"ЭО","ЭО","ЭО","ЭО","ЭО","ЭО","ЭО"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","Вх. дверь","План",null,null,null,null,null,null,null,null,null,null,"Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь","Вх. дверь"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"СС","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"СС","СС","СС","СС","СС","СС","СС"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"ФР для отд.","План",null,null,null,null,null,null,null,null,null,null,null,"ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Черн. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"ЭО","План",null,null,null,null,null,null,null,null,null,"ЭО","ЭО","ЭО","ЭО","ЭО","ЭО","ЭО"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
["Корпус 6.2","012. Монолитные приямки","ГПК Инжпетрострой (монолит)","Секция 4","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 5","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 10","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"016. ● Подвал. Трубопровод ливневой канализации","СК ИнжСтрой","Секция 1","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"017. ● Подвал. Трубопровод хоз.-быт. канализации","СК ИнжСтрой","Секция 1","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"018. ● Подвал. Трубопровод системы водоснабжения","СК ИнжСтрой","Секция 1","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"019. ● Подвал. Трубопровод системы отопления","СК ИнжСтрой","Секция 1","п","План",null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,75,75,75,75,75,75,75]
[null,"033. Монтаж вентиляционных отводов с/у","СК ИнжСтрой","Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 9","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 10","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"034. Отверстия и трубы КИВ","СК ИнжСтрой","Секция 1","1","План",null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,100,100,100,100,100,100,100]
[null,null,null,null,"2","План",null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,100,100,100,100,100,100,100]
[null,null,null,null,"3","План",null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,100,100,100,100,100,100,100]
[null,null,null,null,"4","План",null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,100,100,100,100,100,100,100]
[null,null,null,"Секция 3","2","План",null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,100,100,100,100,100,100,100]
[null,null,null,null,"3","План",null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,100,100,100,100,100,100,100]
[null,null,null,null,"4","План",null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,100,100,100,100,100,100,100]
[null,null,null,"Секция 9","1","План",1,1]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,null,"2","План",2,2]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,null,"3","План",3,3]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,null,"4","План",4,4]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,"Секция 10","1","План",1,1,1]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,null,"2","План",2,2,2]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,null,"3","План",3,3,3]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,null,"4","План",4,4,4]
[null,null,null,null,null,"Факт",100,100,100]
[null,"035. Линейный монтаж проводов ЭО квартир","ГПК Инжпетрострой (электрика)","Секция 9","3","План",3,3,3,3]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,100,100,100,100]
[null,"036. Линейный монтаж АППЗ квартир и МОП","(пусто)","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 2","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 3","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 4","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 5","2","План",null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 6","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 10","1","План",null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,"039. ▌Фасады на балконах. Утепление","СУ Эдельвейс","Секция 1","1","План",1]
[null,null,null,null,null,"Факт",100]
[null,null,null,null,"2","План",2,2]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,null,"3","План",3,3,3]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,null,"4","План",4,4,4,4]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,null,null,"Секция 2","2","План",2,2,2,2]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,null,null,null,"3","План",3,3,3,3,3]
[null,null,null,null,null,"Факт",100,100,100,100,100]
[null,null,null,null,"4","План",4,4,4,4,4,4]
[null,null,null,null,null,"Факт",100,100,100,100,100,100]
[null,null,null,"Секция 3","2","План",2,2,2,2]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,null,null,null,"3","План",3,3,3,3,3]
[null,null,null,null,null,"Факт",100,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 4","2","План",null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 5","4","План",4]
[null,null,null,null,null,"Факт",100]
[null,null,null,"Секция 6","4","План",4,4,4,4]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,null,null,"Секция 9","4","План",null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,100,100,100,100,100,100,100]
[null,null,null,"Секция 10","1","План",null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,100,100,100,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,100,100,100,100,100,100,100]
[null,"040. ▌Фасады на балконах. Армировка","СУ Эдельвейс","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","2","План",null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 3","2","План",null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 4","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 5","4","План",null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","2","План",null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,100,100,100,100,100,100,100]
[null,null,null,null,"3","План",null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,100,100,100,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 9","1","План",null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 10","1","План",null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"041. ▌Фасады на балконах. Декор","СУ Эдельвейс","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 3","2","План",null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 4","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 5","4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","2","План",null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 7","4","План",4]
[null,null,null,null,null,"Факт",100]
[null,null,null,"Секция 8","4","План",4]
[null,null,null,null,null,"Факт",100]
[null,null,null,"Секция 9","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 10","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"060. Штукатурка стен вкруг и потолков","(пусто)","Секция 5","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,"Фаст Компани","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,"Секция 3","2","План",null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,10,10,10,10,10,10,10]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0]
[null,null,null,"Секция 10","1","План",null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0]
[null,"061. Штукатурка лестниц","(пусто)","Секция 5","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,"Фаст Компани","Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 10","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,"062. Монтаж радиаторов","СК ИнжСтрой","Секция 3","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 5","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 10","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,"063. Монтаж коллекторов","СК ИнжСтрой","Секция 3","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 5","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,"064. Монтаж подложки под PEX","(пусто)","Секция 5","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,"Фаст Компани","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 3","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 10","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,"065. Монтаж PEX","СК ИнжСтрой","Секция 3","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 5","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 10","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,"066. Пневмоиспытания труб отопления","СК ИнжСтрой","Секция 3","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 5","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 10","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,"067. Стяжка квартир и МОП","(пусто)","Секция 5","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,"Фаст Компани","Секция 3","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 10","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,"070. ▌Фасады с лесов. Утепление","СУ Эдельвейс","Секция 1","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 3","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 4","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 6","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,"Секция 7","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 8","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,50,50,50,50,50,50,50]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,50,50,50,50,50,50,50]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,50,50,50,50,50,50,50]
[null,null,null,"Секция 9","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,"071. ▌Фасады с лесов. Армировка","СУ Эдельвейс","Секция 1","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 2","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 3","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 6","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 7","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 8","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 9","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,"072. ▌Фасады с лесов. Декор","СУ Эдельвейс","Секция 1","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 2","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 3","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 6","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 8","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,"086. Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)","Секция 3","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 5","2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,"Секция 10","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,"144. Водомерный узел","(пусто)","Секция 6","Монт. обор.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Монт. обор.","Монт. обор.","Монт. обор.","Монт. обор.","Монт. обор.","Монт. обор.","Монт. обор."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Постав. обор.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Постав. обор.","Постав. обор.","Постав. обор.","Постав. обор.","Постав. обор.","Постав. обор.","Постав. обор."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"145. Насосная","(пусто)","Секция 6","Постав. обор.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Постав. обор.","Постав. обор.","Постав. обор.","Постав. обор.","Постав. обор.","Постав. обор."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0]
["Корпус 6.3","012. Монолитные приямки","ГПК Инжпетрострой (монолит)","Секция 4","п","План",null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 5","п","План",null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 8","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"015. ● Подвал. Лотки ЭО","ГПК Инжпетрострой (электрика)","Секция 2","п","План",null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,100,100,100,100,100]
[null,null,null,"Секция 3","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,50,50,50,50,50]
[null,null,null,"Секция 4","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,"Секция 5","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,"Секция 6","п","План",null,"п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,100,100,100,100,100]
[null,"018. ● Подвал. Трубопровод системы водоснабжения","ГПК Инжпетрострой (сантехника)","Секция 1","п","План",null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,"Секция 3","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 4","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 5","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,"019. ● Подвал. Трубопровод системы отопления","ГПК Инжпетрострой (сантехника)","Секция 4","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 5","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"027. Кладка наружных стен","ГПК Инжпетрострой (кладка)","Секция 4","1","План",null,null,1,1,1,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,100,100,100,100,100,100,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,90,90,90,90,90,90,90,90,90,90]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,90,90,90,90,90,90,90,90,90,90]
[null,null,null,"Секция 5","1","План",1,1,1,1,1]
[null,null,null,null,null,"Факт",100,100,100,100,100]
[null,null,null,null,"2","План",2,2,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",100,100,100,100,100,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,3,3,3,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,100,100,100,100,100,100,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100,100,100,100]
[null,null,null,"Секция 6","1","План",1,1,1,1]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,null,null,null,"2","План",2,2,2,2]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,null,null,null,"3","План",3,3,3,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",100,100,100,100,100,100,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,null,4,4,4,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,100,100,100,100,100,100,100,100,100,100]
[null,null,null,"Секция 7","3","План",3,3,3]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,null,"4","План",4,4,4,4]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,"028. Кладка внутренних стен и перегородок","ГПК Инжпетрострой (кладка)","Секция 4","1","План",null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,75,75,75,75,75,75,75]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,25,25,25,25,25,25,25]
[null,null,null,null,"кр","План","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",100,100,100,100,100]
[null,null,null,null,"п","План","п","п","п"]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,"Секция 5","1","План",1,1,1,1,1]
[null,null,null,null,null,"Факт",100,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,"Секция 6","1","План",1,1,1,1]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,null,null,null,"2","План",2,2,2,2]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,"Секция 7","3","План",3,3,3]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,null,"4","План",4,4,4,4,4]
[null,null,null,null,null,"Факт",100,100,100,100,100]
[null,null,null,null,"п","План",null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,100,100,100,100,100,100,100]
[null,"029. Кладка шиделей (штучных вентблоков)","ГПК Инжпетрострой (кладка)","Секция 4","3","План",3]
[null,null,null,null,null,"Факт",100]
[null,null,null,null,"4","План",4,4,4]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,null,"кр","План","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,null,null,"Секция 5","2","План",null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,"Секция 6","3","План",3,3,3,3,3,3]
[null,null,null,null,null,"Факт",100,100,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,100,100,100,100,100,100,100]
[null,"030. Монтаж окон","СК Козерог","Секция 2","4","План",4]
[null,null,null,null,null,"Факт",100]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,25,25,25,25,25,25,25]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,25,25,25,25,25,25,25]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,25,25,25,25,25,25,25]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,25,25,25,25,25,25,25]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,"031. Стояки ВК квартирные","ГПК Инжпетрострой (сантехника)","Секция 3","4","План",4]
[null,null,null,null,null,"Факт",100]
[null,null,null,"Секция 5","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 6","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"032. Водорозетки","ГПК Инжпетрострой (сантехника)","Секция 3","1","План",1,1]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,null,"2","План",2,2]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,null,"3","План",3,3,3]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,null,"4","План",4,4,4]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,"Секция 6","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"034. Отверстия и трубы КИВ","ГПК Инжпетрострой (сантехника)","Секция 5","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,"Секция 8","1","План",1,1]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,null,"2","План",2,2]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,null,"3","План",3,3,3]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,null,"4","План",4,4]
[null,null,null,null,null,"Факт",100,100]
[null,"035. Линейный монтаж проводов ЭО квартир","ГПК Инжпетрострой (электрика)","Секция 2","1","План",1,1,1]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,null,"2","План",2,2,2]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 8","1","План",1,1,1,1]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,"036. Линейный монтаж АППЗ квартир и МОП","(пусто)","Секция 1","1","План",null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,"Секция 2","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,50,50,50,50]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,50,50,50,50]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,50,50,50,50]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,50,50,50,50]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,50,50,50]
[null,"038. Затяжка проводов ЭО лестниц","ГПК Инжпетрострой (электрика)","Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 4","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 5","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"039. ▌Фасады на балконах. Утепление","Арсенал Строй","Секция 1","4","План",4,4,4,4]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,null,null,"Секция 2","2","План",2,2,2,2]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,null,null,null,"3","План",null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,100,100,100,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,"Секция 3","1","План",null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,100,100,100,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,"Секция 6","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,"040. ▌Фасады на балконах. Армировка","Арсенал Строй","Секция 1","1","План",null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,"Секция 2","1","План",null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,100,100,100,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0]
[null,"041. ▌Фасады на балконах. Декор","Арсенал Строй","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,"045. ▲ Кровля. Монтаж вентиляторов на кровле","ГПК Инжпетрострой (сантехника)","Секция 1","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 3","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 4","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 5","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 7","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 8","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"046. ▲ Кровля. Пароизоляция","МОСТ-СПБ","Секция 4","кр","План",null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,100,100,100,100,100,100,100]
[null,null,null,"Секция 5","кр","План",null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,100,100,100,100,100,100,100]
[null,"047. ▲ Кровля. Теплоизоляция","МОСТ-СПБ","Секция 3","кр","План","кр","кр","кр"]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,"Секция 4","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 5","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 7","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 8","кр","План",null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,"048. ▲ Кровля. Стяжка, воронки","МОСТ-СПБ","Секция 1","кр","План",null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,100,100,100,100,100,100,100]
[null,null,null,"Секция 2","кр","План",null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,100,100,100,100,100,100,100]
[null,null,null,"Секция 3","кр","План",null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,100,100,100,100,100,100,100]
[null,null,null,"Секция 4","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 5","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 7","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 8","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,"049. ▲ Кровля. Гидроизоляция нижний слой","МОСТ-СПБ","Секция 1","кр","План",null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 3","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 7","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 8","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"050. ▲ Кровля. Гидроизоляция вентшахт","МОСТ-СПБ","Секция 1","кр","План",null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 3","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 7","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 8","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"056. Кабельные линии ЭО фасадов","ГПК Инжпетрострой (электрика)","Секция 1","1","План",1,1,1,1]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,null,null,"Секция 2","1","План",null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,100,100,100,100,100,100,100]
[null,null,null,"Секция 3","1","План",null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,"Секция 4","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,"Секция 5","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,"Секция 6","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,50,50,50,50,50,50,50]
[null,"060. Штукатурка стен вкруг и потолков","(пусто)","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 2","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,"062. Монтаж радиаторов","ГПК Инжпетрострой (сантехника)","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 2","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,"065. Монтаж PEX","ГПК Инжпетрострой (сантехника)","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 2","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,"066. Пневмоиспытания труб отопления","ГПК Инжпетрострой (сантехника)","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 2","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,"067. Стяжка квартир и МОП","(пусто)","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 2","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,"070. ▌Фасады с лесов. Утепление","Арсенал Строй","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,"073. ▌Фасады НВФ. Кронштейны","(пусто)","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0]
[null,null,null,"Секция 2","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0]
[null,null,null,"Секция 4","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0]
[null,null,null,"Секция 5","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0]
[null,null,null,"Секция 6","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0]
[null,"082. Металлические ограждения лестниц","(пусто)","Секция 2","4","План",4]
[null,null,null,null,null,"Факт",100]
[null,null,null,"Секция 3","4","План",4,4]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,"Секция 4","1","План",1,1,1,1]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,null,null,null,"2","План",2,2,2,2]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,null,null,null,"3","План",3,3,3,3]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,null,null,null,"4","План",4,4,4,4]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,null,null,"Секция 5","1","План",1,1,1]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,null,"2","План",2,2,2]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,null,"3","План",3,3,3]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,null,"4","План",4,4,4]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,"Секция 6","1","План",1,1]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,null,"2","План",2,2]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,null,"3","План",3,3]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,null,"4","План",4,4]
[null,null,null,null,null,"Факт",100,100]
[null,"086. Вмазка коробок и квартирных щитов","ГПК Инжпетрострой (электрика)","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,null,null,"Секция 2","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,"144. Водомерный узел","(пусто)","Секция 3","Монт. обор.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Монт. обор.","Монт. обор.","Монт. обор.","Монт. обор.","Монт. обор.","Монт. обор.","Монт. обор."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Постав. обор.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Постав. обор.","Постав. обор.","Постав. обор.","Постав. обор.","Постав. обор.","Постав. обор.","Постав. обор."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"145. Насосная","(пусто)","Секция 3","Монт. обор.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Монт. обор.","Монт. обор.","Монт. обор.","Монт. обор.","Монт. обор.","Монт. обор."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0]
["Корпус 6.4","008. Гидроизоляция цоколя","Гидроизол","Секция 4","п","План","п","п","п"]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,"Секция 6","п","План","п","п","п"]
[null,null,null,null,null,"Факт",100,100,100]
[null,"009. Утепление цоколя","ГПК Инжпетрострой (монолит)","Секция 1","п","План","п","п"]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,"Секция 3","п","План","п"]
[null,null,null,null,null,"Факт",100]
[null,null,null,"Секция 4","п","План",null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,0,0,0,0,0,0,0,0,0,0]
[null,null,null,"Секция 5","п","План","п","п"]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,"Секция 6","п","План","п","п","п","п","п"]
[null,null,null,null,null,"Факт",100,100,100,100,100]
[null,"012. Монолитные приямки","ГПК Инжпетрострой (монолит)","Секция 1","п","План",null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","п","План",null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 3","п","План",null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 4","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 5","п","План",null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","п","План",null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 7","п","План",null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 8","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"017. ● Подвал. Трубопровод хоз.-быт. канализации","ГПК Инжпетрострой (сантехника)","Секция 3","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,75,75,75,75,75]
[null,null,null,"Секция 8","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"018. ● Подвал. Трубопровод системы водоснабжения","ГПК Инжпетрострой (сантехника)","Секция 1","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 8","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0]
[null,"019. ● Подвал. Трубопровод системы отопления","ГПК Инжпетрострой (сантехника)","Секция 1","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"022. Утепление фасада под балконами","СУ Эдельвейс","Секция 1","п","План",null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","п","План",null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 3","п","План",null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 4","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 5","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 7","п","План",null,null,null,null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 8","п","План",null,null,null,null,null,null,null,null,null,null,"п","п","п","п","п","п","п"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"027. Кладка наружных стен","ГПК Инжпетрострой (кладка)","Секция 8","4","План",4]
[null,null,null,null,null,"Факт",100]
[null,"030. Монтаж окон","СК Козерог","Секция 1","1","План",null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,"Секция 2","1","План",1,1,1,1]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,null,null,null,"2","План",2,2,2,2,2]
[null,null,null,null,null,"Факт",100,100,100,100,100]
[null,null,null,null,"3","План",3,3,3,3,3,3]
[null,null,null,null,null,"Факт",100,100,100,100,100,100]
[null,null,null,null,"4","План",null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,100,100,100,100,100,100,100]
[null,null,null,"Секция 3","1","План",1,1]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,null,"2","План",2,2,2]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,null,"3","План",3,3,3]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,null,"4","План",4,4,4,4]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"031. Стояки ВК квартирные","ГПК Инжпетрострой (сантехника)","Секция 1","1","План",null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","4","План",4]
[null,null,null,null,null,"Факт",100]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"032. Водорозетки","ГПК Инжпетрострой (сантехника)","Секция 1","1","План",null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","1","План",1,1]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,null,"2","План",2,2]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,null,"3","План",3,3]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,null,"4","План",4,4]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"034. Отверстия и трубы КИВ","ГПК Инжпетрострой (сантехника)","Секция 8","1","План",null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,100,100,100,100,100,100,100]
[null,"035. Линейный монтаж проводов ЭО квартир","ГПК Инжпетрострой (электрика)","Секция 1","2","План",2,2]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,100,100,100,100]
[null,null,null,"Секция 3","3","План",3,3]
[null,null,null,null,null,"Факт",100,100]
[null,null,null,null,"4","План",4,4,4]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,"Секция 8","1","План",null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,100,100,100,100]
[null,"036. Линейный монтаж АППЗ квартир и МОП","(пусто)","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 4","1","План",1,1,1,1]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,50,50,50,50]
[null,null,null,"Секция 5","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,"Секция 6","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 7","1","План",1,1,1,1]
[null,null,null,null,null,"Факт",100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,100,100,100,100]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0]
[null,"039. ▌Фасады на балконах. Утепление","СУ Эдельвейс","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","1","План",null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"040. ▌Фасады на балконах. Армировка","СУ Эдельвейс","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 4","1","План",1,1,1]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,null,"2","План",2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",100,100,100,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,100,100,100,100,100,100,100]
[null,null,null,null,"4","План",4,4,4]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"041. ▌Фасады на балконах. Декор","СУ Эдельвейс","Секция 1","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 2","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 3","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 4","1","План",null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 5","1","План",1,1,1,1,1]
[null,null,null,null,null,"Факт",100,100,100,100,100]
[null,null,null,null,"2","План",2,2,2,2,2]
[null,null,null,null,null,"Факт",100,100,100,100,100]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","1","План",null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2,2,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3,3,3,3,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"4","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4,4,4,4,4,4]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0]
[null,"045. ▲ Кровля. Монтаж вентиляторов на кровле","ГПК Инжпетрострой (сантехника)","Секция 1","кр","План",null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,100,100,100,100,100,100,100]
[null,null,null,"Секция 5","кр","План","кр","кр","кр"]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,"Секция 6","кр","План","кр","кр","кр"]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,"Секция 7","кр","План","кр","кр","кр"]
[null,null,null,null,null,"Факт",100,100,100]
[null,null,null,"Секция 8","кр","План",null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,100,100,100,100,100,100,100]
[null,"046. ▲ Кровля. Пароизоляция","МитраЛад","Секция 8","кр","План",null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,100,100,100,100,100,100,100]
[null,"047. ▲ Кровля. Теплоизоляция","МитраЛад","Секция 8","кр","План",null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"048. ▲ Кровля. Стяжка, воронки","МитраЛад","Секция 8","кр","План",null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"049. ▲ Кровля. Гидроизоляция нижний слой","МитраЛад","Секция 1","кр","План","кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",100,100,100,100,100,100,100]
[null,null,null,"Секция 2","кр","План",null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 8","кр","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"кр","кр","кр","кр","кр","кр","кр"]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"060. Штукатурка стен вкруг и потолков","(пусто)","Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,1,1,1,1,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"062. Монтаж радиаторов","ГПК Инжпетрострой (сантехника)","Секция 4","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 5","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,"065. Монтаж PEX","ГПК Инжпетрострой (сантехника)","Секция 4","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 5","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,"066. Пневмоиспытания труб отопления","ГПК Инжпетрострой (сантехника)","Секция 4","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 5","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,"Секция 7","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,null,null,"Секция 8","1","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1,1]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"2","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2,2]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0]
[null,null,null,null,"3","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0]
[null,"142. ИТП жилых помещений","(пусто)","Секция 3","ФР для отд.","План",null,null,null,null,null,null,null,null,null,null,"ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"144. Водомерный узел","(пусто)","Секция 7","ФР для отд.","План",null,null,null,null,null,null,null,null,null,null,"ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Черн. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"145. Насосная","(пусто)","Секция 7","Монт. обор.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Монт. обор.","Монт. обор.","Монт. обор.","Монт. обор.","Монт. обор.","Монт. обор.","Монт. обор."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"ФР для отд.","План",null,null,null,null,null,null,null,null,null,null,"ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,null,"Черн. отд.","План",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд.","Черн. отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"146. Кабельная","(пусто)","Секция 1","ФР для отд.","План",null,null,null,null,null,null,null,null,null,null,null,"ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","ФР для отд.","План",null,null,null,null,null,null,null,null,null,null,null,"ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,"149. ГРЩ","(пусто)","Секция 1","ФР для отд.","План",null,null,null,null,null,null,null,null,null,null,null,"ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]
[null,null,null,"Секция 6","ФР для отд.","План",null,null,null,null,null,null,null,null,null,null,null,"ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд.","ФР для отд."]
[null,null,null,null,null,"Факт",null,null,null,null,null,null,null,null,null,null,null,0,0,0,0,0,0,0]